## I_Inputs & Assumptions
CONSTRUCTION-TO-PERMANENT FINANCIAL MODEL
INPUTS & ASSUMPTIONS
PROJECT INFORMATION
Project Name | Campus Adele
Location | Quebec
Construction Start Date | 2025-03-01
Construction Duration | 13 | months
Months Until First Units Ready | 16 | months
Gap to Permanent Financing | 1 | months
Permanent Loan Term | 60 | months
Exit Timing (Post-Construction) | 61 | months
CONSTRUCTION BUDGET
Land - Purchase Price | 400000
Land - Recognized Value | 600000
Assessed Property Value | 15000000
Hard Costs by Category | Budget | Phasing % | Holdback % | Release (mo)
Site Work & Demolition | 500000 | Equal | 10% | 3
Foundation & Structure | 3000000 | Front-loaded | 10% | 2
Building Envelope | 2000000 | Mid-weighted | 10% | 3
MEP Systems | 2500000 | Mid-weighted | 10% | 4
Interior Finishes | 1500000 | Back-loaded | 10% | 2
Landscaping & Site | 300000 | Back-loaded | 10% | 6
Soft Costs by Category | Budget | Holdback %
Architecture & Engineering | 400000 | 10%
Permits & Approvals | 150000 | 0%
Legal & Financing Fees | 200000 | 0%
Development Management | 300000 | 10%
Marketing & Leasing | 100000 | 0%
Contingency | 500000
CONSTRUCTION FINANCING - SENIOR LOAN
Loan-to-Cost (LTC) % | 77.19% | %
Interest Rate (Annual) | 4.95% | %
Commitment Fee | 0.1% | %
Loan Amount | 33627000 | %
SUBORDINATED LOAN #1 - PREFERRED EQUITY
Loan Amount | 0
Interest Rate (Annual) | 8% | %
Commitment Fee | 0.1% | %
Draw Priority | 1
SUBORDINATED LOAN #2 - MEZZANINE
Loan Amount | 0
Interest Rate (Annual) | 10% | %
Commitment Fee | 0.1% | %
Draw Priority | 2
GST/QST
CASH MANAGEMENT | 5% | %
Minimum Cash Balance | 100000 | Target minimum cash to maintain
Sales Tax LOC Limit | 750000 | Maximum Sales Tax LOC
GST/QST LOC Facility Size | 750000
PERMANENT FINANCING
Permanent Loan Amount | 19000000 | $
CMB Rate | 3.29% | %
Markup | 0.45% | %
Contingency | 0% | %
Total Interest Rate | 3.74% | %
Amortization Period | 50 | years
DSCR Covenant Minimum | 1.1 | x
EQUITY
Class E (LP) Total Commitment | 2800000
Class A (GP) Land Contribution | 0 | (recognized value)
Preferred Return % (Annual) | 0% | %
REVENUE ASSUMPTIONS
Total Parking Spaces | 47
Revenue-Generating Parking Spaces | 47
Parking Rate | 75 | $/month
Internet Rate per Unit | 50 | $/month
EV Charging Stations | 50
EV Charging Rate | 38 | $/month
Annual Revenue Growth | 2% | %
Lease-Up Lag (Months) | 2 | months
Stabilized Vacancy % | 6% | %
Service Revenue Escalation | 1.5% | %
OPERATING EXPENSES
Municipal Tax - Mill Rate | 0.75% | %
School Tax - Mill Rate | 0.156% | %
Tax Start Delay (Post-Construction) | 0 | months
Tax Assessment Escalation | 0% | %
Operating Expense Line Items | Annual Amount | Escalation %
Insurance | 16989 | 1%
Repairs & Maintenance | 38400 | 1%
Outdoor Amenities Maintenance | 2000 | 1%
Snow Removal, Grass, Garbage | 23000 | 1%
Janitor | 23000 | 1%
Cleaning Reserve on Turnover | 7650 | 1%
Security & Monitoring | 9000 | 1%
Internet | 20000 | 1%
EV Charging Stations | 5000 | 1%
Electricity (Common) | 12200 | 1%
Administration (% of EGI) | 3% | 0%
RESERVES |  |  | Escalation %
Appliance/Furniture Reserve | 700 | $/unit/year | 1%
Structural Reserve | 0.75% | % of EGI | 1%
DISTRIBUTIONS
Minimum Cash Balance | 100000
Distribution Frequency | Quarterly
Waterfall Structure
Tier 1: Preferred Return % | 0% | % (annual)
Tier 2: Return of Capital | 100%
Tier 3: Profit Split - Class E (LP) | 70% | %
Tier 3: Profit Split - Class A (GP) | 30% | %
EXIT
Exit Cap Rate | 4.5% | %
Disposition Costs | 1% | % of sale price
Other Exit Costs | 0

## I_Budget Input Data
BUDGET INPUT DATA
Imported from ryanbudget.csv - Edit phasing, holdback, and eligibility as needed
Row # | Category | Subcategory | Budget Amount | Phasing Pattern | Holdback % | Holdback Release (mo after constr) | GST/QST Eligible
1 |  |  | 0 | Equal | 10% | 3 | Yes
2 | 1. LAND | Land Acquisition | 1600000 | Upfront | 0% | 0 | Yes
3 | 1. LAND | Notary and cadastre | 19808 | Upfront | 0% | 0 | Yes
4 | 1. LAND | Cadastral operation | 105360 | Upfront | 0% | 0 | Yes
5 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Adjustment for Bldgs 5 & 6 | 479320 | Front-loaded | 10% | 3 | Yes
6 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Trailer pad, Access road, Septic tank | 10900 | Front-loaded | 10% | 3 | Yes
7 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Credit - Reservoir change | 1946765 | Front-loaded | 10% | 3 | Yes
8 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Credit - Reservoir change | 0 | Front-loaded | 10% | 3 | Yes
9 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Campus Civil | 143113 | Front-loaded | 10% | 3 | Yes
10 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Campus Civil | 30493 | Front-loaded | 10% | 3 | Yes
11 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & backfill - Extension - Mtee Ryan Civil | 375295 | Front-loaded | 10% | 3 | Yes
12 | 2. SITE SERVICING + LANDSCAPE |  | 165563 | Front-loaded | 10% | 3 | Yes
13 | 2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 475672 | Front-loaded | 10% | 3 | Yes
14 | 2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 23100 | Front-loaded | 10% | 3 | Yes
15 | 2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 2300 | Front-loaded | 10% | 3 | Yes
16 | 2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 25102 | Front-loaded | 10% | 3 | Yes
17 | 2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 47223 | Front-loaded | 10% | 3 | Yes
18 | 2. SITE SERVICING + LANDSCAPE | Landscaping:Excavation & Backfill - Landscaping | 1065794 | Front-loaded | 10% | 3 | Yes
19 | 2. SITE SERVICING + LANDSCAPE | Electrical services | 252500 | Front-loaded | 10% | 3 | Yes
20 | 2. SITE SERVICING + LANDSCAPE | Electrical charging stations | 124981 | Front-loaded | 10% | 3 | Yes
21 | 3. HARD COSTS | Admin and profit | 1577987 | Equal | 10% | 3 | Yes
22 | 3. HARD COSTS | Insurance and bonding:Insurance | 278718 | Equal | 10% | 3 | Yes
23 | 3. HARD COSTS |  | 140525 | Equal | 10% | 3 | Yes
24 | 3. HARD COSTS | Insurance and bonding:Wrap-up | 36465 | Equal | 10% | 3 | Yes
25 | 3. HARD COSTS | Insurance and bonding:Bris des Machines | 2585 | Equal | 10% | 3 | Yes
26 | 3. HARD COSTS | Insurance and bonding:L&M and Performance Bonds | 0 | Equal | 10% | 3 | Yes
27 | 3. HARD COSTS | General conditions:CoSS Agent | 236000 | Equal | 10% | 3 | Yes
28 | 3. HARD COSTS | General conditions:RSS Agent | 213500 | Equal | 10% | 3 | Yes
29 | 3. HARD COSTS | General conditions:Superintendent 1 | 303400 | Equal | 10% | 3 | Yes
30 | 3. HARD COSTS | General conditions:Superintendent 2 | 266400 | Equal | 10% | 3 | Yes
31 | 3. HARD COSTS | General conditions:Project Manager | 150750 | Equal | 10% | 3 | Yes
32 | 3. HARD COSTS | General conditions:Labourer | 230020 | Equal | 10% | 3 | Yes
33 | 3. HARD COSTS | General Conditions: Logding | 11000 | Equal | 10% | 3 | Yes
34 | 3. HARD COSTS | General conditions:Site fencing | 10780 | Equal | 10% | 3 | Yes
35 | 3. HARD COSTS | General Conditions: Printing | 8048 | Equal | 10% | 3 | Yes
36 | 3. HARD COSTS | General conditions:Scaffolding-Cranes-Nacelles | 242750 | Equal | 10% | 3 | Yes
37 | 3. HARD COSTS | General conditions:Tool rental | 0 | Equal | 10% | 3 | Yes
38 | 3. HARD COSTS | General conditions:Garbage chutes | 0 | Equal | 10% | 3 | Yes
39 | 3. HARD COSTS | General conditions:Garbage containers | 87875 | Equal | 10% | 3 | Yes
40 | 3. HARD COSTS | General conditions:Site trailers - Rental | 51500 | Equal | 10% | 3 | Yes
41 | 3. HARD COSTS | General conditions:Storage container rental | 8798 | Equal | 10% | 3 | Yes
42 | 3. HARD COSTS | General conditions:Sanitary trailer - Rental/Purchase - Portable Toilets | 56242 | Equal | 10% | 3 | Yes
43 | 3. HARD COSTS | General conditions:Winter conditions | 881840 | Equal | 10% | 3 | Yes
44 | 3. HARD COSTS | General conditions:Camera Security - Equipement | 29000 | Equal | 10% | 3 | Yes
45 | 3. HARD COSTS | General conditions:Camera Security - Monthly surveillance fees | 0 | Equal | 10% | 3 | Yes
46 | 3. HARD COSTS | General conditions:Temporary Electrical - Installation | 147967 | Equal | 10% | 3 | Yes
47 | 3. HARD COSTS | General conditions:Temporary Electrical - Consumption | 0 | Equal | 10% | 3 | Yes
48 | 3. HARD COSTS | General conditions:Trailer & WC maintenance | 6500 | Equal | 10% | 3 | Yes
49 | 3. HARD COSTS | General conditions:Daily cleaning | 60094 | Equal | 10% | 3 | Yes
50 | 3. HARD COSTS | General conditions:Final Cleaning | 53800 | Equal | 10% | 3 | Yes
51 | 3. HARD COSTS | General conditions:Laboratory & Testing | 98600 | Equal | 10% | 3 | Yes
52 | 3. HARD COSTS | General conditions:Surveyor | 35407 | Equal | 10% | 3 | Yes
53 | 3. HARD COSTS | General conditions:Project signage | 181830 | Equal | 10% | 3 | Yes
54 | 3. HARD COSTS |  | 6000 | Equal | 10% | 3 | Yes
55 | 3. HARD COSTS | General conditions:Miscellaneous | 1901 | Equal | 10% | 3 | Yes
56 | 3. HARD COSTS | Formwork:Concrete purchases - Hambro floors | 94276 | Front-loaded | 10% | 3 | Yes
57 | 3. HARD COSTS | Formwork:Stair slab concrete | 27681 | Front-loaded | 10% | 3 | Yes
58 | 3. HARD COSTS | Concrete:Concrete purchases | 97941 | Front-loaded | 10% | 3 | Yes
59 | 3. HARD COSTS | Formwork:Insulated formwork | 2681518 | Front-loaded | 10% | 3 | Yes
60 | 3. HARD COSTS |  | 0 | Equal | 10% | 3 | Yes
61 | 3. HARD COSTS | Formwork:Wire mesh - Hambro floors | 62581 | Front-loaded | 10% | 3 | Yes
62 | 3. HARD COSTS | Formwork:Cement finishing | 163654 | Front-loaded | 10% | 3 | Yes
63 | 3. HARD COSTS | Formwork:Stair slab cement finishing | 0 | Front-loaded | 10% | 3 | Yes
64 | 3. HARD COSTS | Formwork:Stair slab concrete pumps | 0 | Front-loaded | 10% | 3 | Yes
65 | 3. HARD COSTS | Formwork:Concrete pumps | 31715 | Front-loaded | 10% | 3 | Yes
66 | 3. HARD COSTS | Concrete:Concrete pumps | 0 | Front-loaded | 10% | 3 | Yes
67 | 3. HARD COSTS | Concrete:Concrete accessories | 79342 | Front-loaded | 10% | 3 | Yes
68 | 3. HARD COSTS | Concrete:Labour - Accessories | 0 | Front-loaded | 10% | 3 | Yes
69 | 3. HARD COSTS | Concrete:Polyethylene .006 - changed to .010 2024-01-22 | 0 | Front-loaded | 10% | 3 | Yes
70 | 3. HARD COSTS | Concrete:3'' Rigid insulation (4' perimeter) - changed to 2'' Blue | 0 | Front-loaded | 10% | 3 | Yes
71 | 3. HARD COSTS | Concrete:Labour - Rigid insulation | 0 | Front-loaded | 10% | 3 | Yes
72 | 3. HARD COSTS | Concrete:Wet cure | 0 | Front-loaded | 10% | 3 | Yes
73 | 3. HARD COSTS | Formwork:Hambro joists | 494189 | Front-loaded | 10% | 3 | Yes
74 | 3. HARD COSTS | Metal works:Stairs | 682129 | Equal | 10% | 3 | Yes
75 | 3. HARD COSTS | Metal works:Steel bases for balcony columns | 0 | Equal | 10% | 3 | Yes
76 | 3. HARD COSTS | Handrails:Railings | 116664 | Equal | 10% | 3 | Yes
77 | 3. HARD COSTS | Carpentry rough:Miscellaneous carpentry labour (DCL) | 754800 | Equal | 10% | 3 | Yes
78 | 3. HARD COSTS | Formwork:Roof trusses - Labour | 550190 | Front-loaded | 10% | 3 | Yes
79 | 3. HARD COSTS | Carpentry rough:Millwork & WC Acc. Blocking | 252570 | Equal | 10% | 3 | Yes
80 | 3. HARD COSTS | Carpentry rough:Stair rail blocking | 0 | Equal | 10% | 3 | Yes
81 | 3. HARD COSTS | Carpentry rough:OSB Dryguard - Roof | 0 | Mid-weighted | 10% | 3 | Yes
82 | 3. HARD COSTS | Carpentry rough:Materials - small roofs | 498625 | Equal | 10% | 3 | Yes
83 | 3. HARD COSTS | Formwork:Hambro plywood purchases | 0 | Front-loaded | 10% | 3 | Yes
84 | 3. HARD COSTS | Handrails:Balcony structures | 0 | Equal | 10% | 3 | Yes
85 | 3. HARD COSTS | Handrails:Floors | 114000 | Equal | 10% | 3 | Yes
86 | 3. HARD COSTS | Carpentry rough:Roof trusses | 176601 | Mid-weighted | 10% | 3 | Yes
87 | 3. HARD COSTS | Kitchen:Kitchens & vanities (QC) | 844652 | Back-loaded | 10% | 3 | Yes
88 | 3. HARD COSTS |  | 0 | Equal | 10% | 3 | Yes
89 | 3. HARD COSTS | Kitchen:Quartz counters - Purchase | 177900 | Back-loaded | 10% | 3 | Yes
90 | 3. HARD COSTS | Kitchen:Quartz counters - Installation | 0 | Back-loaded | 10% | 3 | Yes
91 | 3. HARD COSTS | Carpentry rough:Roof insulation | 35500 | Mid-weighted | 10% | 3 | Yes
92 | 3. HARD COSTS | Exterior finishes:Wood siding | 1482450 | Mid-weighted | 10% | 3 | Yes
93 | 3. HARD COSTS | Exterior finishes:Acrylic stucco & Duroc | 280000 | Mid-weighted | 10% | 3 | Yes
94 | 3. HARD COSTS | Roof, membrane:Roofing (Shingles) | 280825 | Mid-weighted | 10% | 3 | Yes
95 | 3. HARD COSTS | Roof, membrane:Roofing (Winter conditions) | 0 | Mid-weighted | 10% | 3 | Yes
96 | 3. HARD COSTS | Roof, membrane:Rain Gutters | 36000 | Mid-weighted | 10% | 3 | Yes
97 | 3. HARD COSTS | Fenestration:Caulking | 91200 | Mid-weighted | 10% | 3 | Yes
98 | 3. HARD COSTS | Doors and hardware:Wood doors | 449827 | Equal | 10% | 3 | Yes
99 | 3. HARD COSTS |  | 49800 | Equal | 10% | 3 | Yes
100 | 3. HARD COSTS |  | 157600 | Equal | 10% | 3 | Yes
101 | 3. HARD COSTS | Carpentry finish:Carpentry | 248100 | Equal | 10% | 3 | Yes
102 | 3. HARD COSTS | Doors and hardware:Baseboard, 1/4-round & casing | 108850 | Equal | 10% | 3 | Yes
103 | 3. HARD COSTS | Carpentry finish:Shelving & Finish materials | 0 | Equal | 10% | 3 | Yes
104 | 3. HARD COSTS | Fenestration:Windows & patio-doors - Supply | 851388 | Mid-weighted | 10% | 3 | Yes
105 | 3. HARD COSTS | Fenestration:Transport & Handling - Quebec | 0 | Mid-weighted | 10% | 3 | Yes
106 | 3. HARD COSTS | Interior systems:Drywall | 2345879 | Back-loaded | 10% | 3 | Yes
107 | 3. HARD COSTS | Ceramic:Ceramic Purchase, Transport, Handling & Installation | 179184 | Back-loaded | 10% | 3 | Yes
108 | 3. HARD COSTS | Ceramic:Shower walls | 0 | Back-loaded | 10% | 3 | Yes
109 | 3. HARD COSTS | Ceramic:Bathroom floors (SPC) | 208859 | Back-loaded | 10% | 3 | Yes
110 | 3. HARD COSTS | Floor covering:Vinyl flooring & Transport, Handling | 343300 | Back-loaded | 10% | 3 | Yes
111 | 3. HARD COSTS |  | 0 | Equal | 10% | 3 | Yes
112 | 3. HARD COSTS | Paint:Painting | 366000 | Back-loaded | 10% | 3 | Yes
113 | 3. HARD COSTS |  | 102000 | Equal | 10% | 3 | Yes
114 | 3. HARD COSTS |  | 0 | Equal | 10% | 3 | Yes
115 | 3. HARD COSTS | Railings:Foot grilles | 0 | Equal | 10% | 3 | Yes
116 | 3. HARD COSTS | Railings:Interior signage | 15300 | Back-loaded | 10% | 3 | Yes
117 | 3. HARD COSTS | Railings:WC acccessories | 25750 | Equal | 10% | 3 | Yes
118 | 3. HARD COSTS | Plumbing:Plumbing (Rough S/I; Finish I/O) | 1643900 | Mid-weighted | 10% | 3 | Yes
119 | 3. HARD COSTS | Plumbing:Plumbing finishes (S) - Toilet, Shower | 377966 | Mid-weighted | 10% | 3 | Yes
120 | 3. HARD COSTS | Fire protection:Extinguishers | 25500 | Equal | 10% | 3 | Yes
121 | 3. HARD COSTS | HVAC:HVAC | 790030 | Mid-weighted | 10% | 3 | Yes
122 | 3. HARD COSTS | Electricity:Electricity | 1866337 | Mid-weighted | 10% | 3 | Yes
123 | 3. HARD COSTS | Electricity:Lighting allowance | 53300 | Mid-weighted | 10% | 3 | Yes
124 | 3. HARD COSTS | Electricity:Transport & Handling - Quebec | 0 | Mid-weighted | 10% | 3 | Yes
125 | 3. HARD COSTS | Electricity:DEL Comptoirs (cuisines) | 0 | Mid-weighted | 10% | 3 | Yes
126 | 4. FF&E | Appliances | 403998 | Back-loaded | 5% | 3 | Yes
127 | 4. FF&E | Casegoods | 963770 | Back-loaded | 5% | 3 | Yes
128 | 4. FF&E | Smallwares | 250000 | Back-loaded | 5% | 3 | Yes
129 | 4. FF&E | Electronic Technology | 175000 | Back-loaded | 5% | 3 | Yes
130 | 5. PROFESSIONAL FEES | Accounting/bookkeeping | 49979 | Front-loaded | 10% | 3 | Yes
131 | 5. PROFESSIONAL FEES | Acoustical | 6740 | Front-loaded | 10% | 3 | Yes
132 | 5. PROFESSIONAL FEES | Appraisal/feasibility study | 67509 | Front-loaded | 10% | 3 | Yes
133 | 5. PROFESSIONAL FEES | Architect-design | 31063 | Front-loaded | 10% | 3 | Yes
134 | 5. PROFESSIONAL FEES | Architecture | 594877 | Front-loaded | 10% | 3 | Yes
135 | 5. PROFESSIONAL FEES | Development services fees | 1325000 | Front-loaded | 10% | 3 | Yes
136 | 5. PROFESSIONAL FEES | Engineer - civil | 227656 | Front-loaded | 10% | 3 | Yes
137 | 5. PROFESSIONAL FEES | Engineer - electrical | 0 | Front-loaded | 10% | 3 | Yes
138 | 5. PROFESSIONAL FEES | Engineer - geothermal | 0 | Front-loaded | 10% | 3 | Yes
139 | 5. PROFESSIONAL FEES | Engineer - mechanical | 89984 | Front-loaded | 10% | 3 | Yes
140 | 5. PROFESSIONAL FEES | Engineer - structural | 158013 | Front-loaded | 10% | 3 | Yes
141 | 5. PROFESSIONAL FEES | Environmental - Phases I/II | 17708 | Front-loaded | 10% | 3 | Yes
142 | 5. PROFESSIONAL FEES | Land survey, certificate of location | 5000 | Front-loaded | 10% | 3 | Yes
143 | 5. PROFESSIONAL FEES | Landscape architect | 81864 | Front-loaded | 10% | 3 | Yes
144 | 5. PROFESSIONAL FEES | Legal | 64523 | Front-loaded | 10% | 3 | Yes
145 | 5. PROFESSIONAL FEES | Marketing/leasing | 297679 | Front-loaded | 10% | 3 | Yes
146 | 5. PROFESSIONAL FEES | Quantity surveyor | 97080 | Front-loaded | 10% | 3 | Yes
147 | 5. PROFESSIONAL FEES | Soil/geotechnical/compaction | 93319 | Front-loaded | 10% | 3 | Yes
148 | 5. PROFESSIONAL FEES | Urban planner | 56552 | Front-loaded | 10% | 3 | Yes
149 | 5. PROFESSIONAL FEES | Water tests | 4000 | Front-loaded | 10% | 3 | Yes
150 | 5. PROFESSIONAL FEES | Declaration of co-ownership/shared services | 15000 | Front-loaded | 10% | 3 | Yes
151 | 6. FINANCE AND ADMINISTRATION | Carrying costs land | 240000 | Equal | 0% | 0 | Yes
152 | 6. FINANCE AND ADMINISTRATION | Construction interest | 1592483 | Equal | 0% | 0 | Yes
153 | 6. FINANCE AND ADMINISTRATION | Disbursements | 10220 | Equal | 0% | 0 | Yes
154 | 6. FINANCE AND ADMINISTRATION | Insurance | 44753 | Equal | 0% | 0 | Yes
155 | 6. FINANCE AND ADMINISTRATION | Legal fees | 125339 | Equal | 0% | 0 | Yes
156 | 6. FINANCE AND ADMINISTRATION | Lender fees | 112290 | Equal | 0% | 0 | Yes
157 | 6. FINANCE AND ADMINISTRATION | CMHC Insurance Premium | 452241 | Equal | 0% | 0 | Yes
158 | 6. FINANCE AND ADMINISTRATION | Mortage broker | 247344 | Equal | 0% | 0 | Yes
159 | 6. FINANCE AND ADMINISTRATION | Permits | 168546 | Equal | 0% | 0 | Yes
160 | 6. FINANCE AND ADMINISTRATION | Pre Construction Carrying costs | 273134 | Equal | 0% | 0 | Yes
161 | 6. FINANCE AND ADMINISTRATION | Taxes | 10000 | Equal | 0% | 0 | Yes
162 | 7. TAX ASSESSMENT | Self assesement taxes | 2087617 | At Completion | 0% | 0 | Yes
163 | 8. CONTINGENCY ALLOWANCE | Contingency | 500000 | As Needed | 0% | 0 | Yes
164 | 8. CONTINGENCY ALLOWANCE | Contingency Buy Down | 0 | As Needed | 0% | 0 | Yes
165 | 8. CONTINGENCY ALLOWANCE | Contingency Non-Classified | 0 | As Needed | 0% | 0 | Yes
166 | HOLDBACKS |  | 0 | Equal | 10% | 3 | Yes

## I_Unit Rent Roll Data
UNIT RENT ROLL DATA
Exact import from Units-Proforma_View_Tremb.csv
UnitId | UnitRentalTypes | Unit # | Planned Delivery Date for Occupancy | Projected Price Per Bedroom (from UnitRentalTypes) | Projected Rate | Bedroom Count (from UnitRentalTypes) | Units Operations ID
ADELE 1 A-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 1 A-201 | Berlin | 201 |  |  | 2455 |  | ADELE -201
ADELE 1 A-301 | Berlin | 301 |  |  | 2455 |  | ADELE -301
ADELE 1 A-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 1 A-202 | Berlin | 202 |  |  | 2455 |  | ADELE -202
ADELE 1 A-302 | Berlin | 302 |  |  | 2455 |  | ADELE -302
ADELE 1 B-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 1 B-201 | Paris | 201 |  |  | 1639 |  | ADELE -201
ADELE 1 B-202 | New York | 202 |  |  | 1589 |  | ADELE -202
ADELE 1 B-301 | Paris | 301 |  |  | 1639 |  | ADELE -301
ADELE 1 B-302 | New York | 302 |  |  | 1589 |  | ADELE -302
ADELE 1 B-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 1 B-202 | Paris | 202 |  |  | 1639 |  | ADELE -202
ADELE 1 B-203 | New York | 203 |  |  | 1589 |  | ADELE -203
ADELE 1 B-302 | Paris | 302 |  |  | 1639 |  | ADELE -302
ADELE 1 C-303 | New York | 303 |  |  | 1589 |  | ADELE -303
ADELE 1 C-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 1 C-201 | Berlin | 201 |  |  | 2455 |  | ADELE -201
ADELE 1 C-301 | Berlin | 301 |  |  | 2455 |  | ADELE -301
ADELE 1 C-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 2 D-303 | New York | 303 |  |  | 1589 |  | ADELE -303
ADELE 2 D-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 2 E-302 | Berlin | 302 |  |  | 2455 |  | ADELE -302
ADELE 2 D-301 | Berlin | 301 |  |  | 2455 |  | ADELE -301
ADELE 1 C-202 | Berlin | 202 |  |  | 2455 |  | ADELE -202
ADELE 2 E-203 | New York | 203 |  |  | 1589 |  | ADELE -203
ADELE 2 D-201 | Paris | 201 |  |  | 1639 |  | ADELE -201
ADELE 2 F-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 2 E-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 2 E-301 | Paris | 301 |  |  | 1639 |  | ADELE -301
ADELE 2 D-302 | Paris | 302 |  |  | 1639 |  | ADELE -302
ADELE 2 E-302 | New York | 302 |  |  | 1589 |  | ADELE -302
ADELE 2 D-202 | Paris | 202 |  |  | 1639 |  | ADELE -202
ADELE 2 D-202 | New York | 202 |  |  | 1589 |  | ADELE -202
ADELE 2 E-201 | Berlin | 201 |  |  | 2455 |  | ADELE -201
ADELE 2 D-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 2 F-201 | Berlin | 201 |  |  | 2455 |  | ADELE -201
ADELE 2 F-301 | Berlin | 301 |  |  | 2455 |  | ADELE -301
ADELE 2 F-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 2 F-202 | Paris | 202 |  |  | 1639 |  | ADELE -202
ADELE 2 F-203 | New York | 203 |  |  | 1589 |  | ADELE -203
ADELE 2 F-302 | Paris | 302 |  |  | 1639 |  | ADELE -302
ADELE 2 F-303 | New York | 303 |  |  | 1589 |  | ADELE -303
ADELE 3 G-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 3 G-201 | Paris | 201 |  |  | 1639 |  | ADELE -201
ADELE 3 G-202 | New York | 202 |  |  | 1589 |  | ADELE -202
ADELE 3 G-301 | Paris | 301 |  |  | 1639 |  | ADELE -301
ADELE 3 G-302 | New York | 302 |  |  | 1589 |  | ADELE -302
ADELE 3 G-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 3 G-202 | Berlin | 202 |  |  | 2455 |  | ADELE -202
ADELE 3 H-301 | Berlin | 301 |  |  | 2455 |  | ADELE -301
ADELE 3 H-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 3 H-201 | Berlin | 201 |  |  | 2455 |  | ADELE -201
ADELE 3 H-302 | Berlin | 302 |  |  | 2455 |  | ADELE -302
ADELE 3 H-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 3 H-202 | Paris | 202 |  |  | 1639 |  | ADELE -202
ADELE 3 H-203 | New York | 203 |  |  | 1589 |  | ADELE -203
ADELE 3 H-302 | Paris | 302 |  |  | 1639 |  | ADELE -302
ADELE 3 H-303 | New York | 303 |  |  | 1589 |  | ADELE -303
ADELE 3 H-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 3 H-201 | Paris | 201 |  |  | 1639 |  | ADELE -201
ADELE 3 H-301 | Paris | 301 |  |  | 1639 |  | ADELE -301
ADELE 3 H-202 | New York | 202 |  |  | 1589 |  | ADELE -202
ADELE 3 H-302 | New York | 302 |  |  | 1589 |  | ADELE -302

## I_Preferred Equity
PREFERRED EQUITY TABLE
Subordinated Loan #1 - Preferred Equity investors
PREFERRED EQUITY INVESTORS
ID | Investor Name | Contribution Amount | Interest Rate | Notes
PE1 |  | 0 | 0%
PE2 |  | 0 | 0%
PE3 |  | 0 | 0%
PE4 |  | 0 | 0%
PE5 |  | 0 | 0%
PE6 |  | 0 | 0%
PE7 |  | 0 | 0%
PE8 |  | 0 | 0%
PE9 |  | 0 | 0%
PE10 |  | 0 | 0%
TOTAL | Preferred Equity |  | Weighted Avg:
INSTRUCTIONS:
• Enter investor names in column B (yellow cells)
• Enter contribution amounts in column C (yellow cells)
• Enter interest rates in column D (yellow cells)
• Add any notes in column E
• Total will update automatically
• This total is linked to Sources & Uses - Construction

## I_Mezzanine Debt
MEZZANINE DEBT TABLE
Subordinated Loan #2 - Mezzanine lenders
MEZZANINE LENDERS
ID | Lender Name | Loan Amount | Interest Rate | Notes
MEZZ1 |  | 0 | 0%
MEZZ2 |  | 0 | 0%
MEZZ3 |  | 0 | 0%
MEZZ4 |  | 0 | 0%
MEZZ5 |  | 0 | 0%
MEZZ6 |  | 0 | 0%
MEZZ7 |  | 0 | 0%
MEZZ8 |  | 0 | 0%
MEZZ9 |  | 0 | 0%
MEZZ10 |  | 0 | 0%
TOTAL | Mezzanine Debt |  | Weighted Avg:
INSTRUCTIONS:
• Enter lender names in column B (yellow cells)
• Enter loan amounts in column C (yellow cells)
• Enter interest rates in column D (yellow cells)
• Add any notes in column E
• Total will update automatically
• This total is linked to Sources & Uses - Construction