## I_Inputs & Assumptions
CONSTRUCTION-TO-PERMANENT FINANCIAL MODEL
INPUTS & ASSUMPTIONS
PROJECT INFORMATION
Project Name | Campus Adele
Location | Quebec
Construction Start Date | 2025-03-01
Construction Duration | 13 | months
Months Until First Units Ready | 16 | months
Gap to Permanent Financing | 1 | months
Permanent Loan Term | 60 | months
Exit Timing (Post-Construction) | 61 | months
CONSTRUCTION BUDGET
Land - Purchase Price | 400000
Land - Recognized Value | 600000
Assessed Property Value | 15000000
Hard Costs by Category | Budget | Phasing % | Holdback % | Release (mo)
Site Work & Demolition | 500000 | Equal | 10% | 3
Foundation & Structure | 3000000 | Front-loaded | 10% | 2
Building Envelope | 2000000 | Mid-weighted | 10% | 3
MEP Systems | 2500000 | Mid-weighted | 10% | 4
Interior Finishes | 1500000 | Back-loaded | 10% | 2
Landscaping & Site | 300000 | Back-loaded | 10% | 6
Soft Costs by Category | Budget | Holdback %
Architecture & Engineering | 400000 | 10%
Permits & Approvals | 150000 | 0%
Legal & Financing Fees | 200000 | 0%
Development Management | 300000 | 10%
Marketing & Leasing | 100000 | 0%
Contingency | 500000
CONSTRUCTION FINANCING - SENIOR LOAN
Loan-to-Cost (LTC) % | 77.19% | % |  |  | SOURCES OF FUNDS | Amount
Interest Rate (Annual) | 4.95% | % |  |  | In disbursement priority order (1→5) | 0
Commitment Fee | 0.1% | % |  |  | 1. Class A Equity (GP - Land Contribution) | 15
Loan Amount | 33627000 | % |  |  | 2. Class E Equity (LP Units) | 2800015
SUBORDINATED LOAN #1 - PREFERRED EQUITY |  |  |  |  | 3. Subordinated Loan #1 (Preferred Equity) | 0
Loan Amount | 0 |  |  |  | 4. Subordinated Loan #2 (Mezzanine) | 0
Interest Rate (Annual) | 8% | % |  |  | 0 | 0
Commitment Fee | 0.1% | % |  |  | Required Additional Equity | 7137311.8725
Draw Priority | 1 |  |  |  | 0 | 0
[5 empty] | 5. Senior Construction Loan | 33628383.1275
SUBORDINATED LOAN #2 - MEZZANINE |  |  |  |  | 0 | 0
Loan Amount | 0 |  |  |  | 0 | 0
Interest Rate (Annual) | 10% | % |  |  | TOTAL SOURCES | 43565725
Commitment Fee | 0.1% | % |  |  | 0 | 0
Draw Priority | 2 |  |  |  | 0 | 0
[5 empty] | USES OF FUNDS | Amount
GST/QST |  |  |  |  | 1. LAND | 1725168
CASH MANAGEMENT | 5% | % |  |  | 2. SITE SERVICING + LANDSCAPE | 5168121
Minimum Cash Balance | 100000 | Target minimum cash to maintain |  |  | 3. HARD COSTS | 25732155
Sales Tax LOC Limit | 750000 | Maximum Sales Tax LOC |  |  | 4. FF&E | 1792768
GST/QST LOC Facility Size | 750000 |  |  |  | 5. PROFESSIONAL FEES | 3283546
[5 empty] | 6. FINANCE AND ADMINISTRATION | 3276350
PERMANENT FINANCING |  |  |  |  | 7. TAX ASSESSMENT | 2087617
Permanent Loan Amount | 19000000 | $ |  |  | 8. CONTINGENCY ALLOWANCE | 500000
CMB Rate | 3.29% | % |  |  | Capitalized Interest | 0
Markup | 0.45% | % |  |  | GST/QST Paid (Gross) | 0
Contingency | 0% | % |  |  | 0 | 0
Total Interest Rate | 3.74% | % |  |  | 0 | 0
Amortization Period | 50 | years |  |  | TOTAL USES | 43565725
DSCR Covenant Minimum | 1.1 | x |  |  | 0 | 0
[5 empty] | 0 | 0
EQUITY |  |  |  |  | RECONCILIATION | 0
Class E (LP) Total Commitment | 2800000 |  |  |  | Total Sources | 43565725
Class A (GP) Land Contribution | 0 | (recognized value) |  |  | Total Uses | 43565725
Preferred Return % (Annual) | 0% | %
REVENUE ASSUMPTIONS
Total Parking Spaces | 47
Revenue-Generating Parking Spaces | 47
Parking Rate | 75 | $/month
Internet Rate per Unit | 50 | $/month
EV Charging Stations | 50
EV Charging Rate | 38 | $/month
Annual Revenue Growth | 2% | %
Lease-Up Lag (Months) | 2 | months
Stabilized Vacancy % | 6% | %
Service Revenue Escalation | 1.5% | %
OPERATING EXPENSES
Municipal Tax - Mill Rate | 0.75% | %
School Tax - Mill Rate | 0.156% | %
Tax Start Delay (Post-Construction) | 0 | months
Tax Assessment Escalation | 0% | %
Operating Expense Line Items | Annual Amount | Escalation %
Insurance | 16989 | 1%
Repairs & Maintenance | 38400 | 1%
Outdoor Amenities Maintenance | 2000 | 1%
Snow Removal, Grass, Garbage | 23000 | 1%
Janitor | 23000 | 1%
Cleaning Reserve on Turnover | 7650 | 1%
Security & Monitoring | 9000 | 1%
Internet | 20000 | 1%
EV Charging Stations | 5000 | 1%
Electricity (Common) | 12200 | 1%
Administration (% of EGI) | 3% | 0%
RESERVES |  |  | Escalation %
Appliance/Furniture Reserve | 700 | $/unit/year | 1%
Structural Reserve | 0.75% | % of EGI | 1%
DISTRIBUTIONS
Minimum Cash Balance | 100000
Distribution Frequency | Quarterly
Waterfall Structure
Tier 1: Preferred Return % | 0% | % (annual)
Tier 2: Return of Capital | 100%
Tier 3: Profit Split - Class E (LP) | 70% | %
Tier 3: Profit Split - Class A (GP) | 30% | %
EXIT
Exit Cap Rate | 4.5% | %
Disposition Costs | 1% | % of sale price
Other Exit Costs | 0

## I_Budget Input Data
BUDGET INPUT DATA
Imported from ryanbudget.csv - Edit phasing, holdback, and eligibility as needed
Row # | Category | Subcategory | Budget Amount | Phasing Pattern | Holdback % | Holdback Release (mo after constr) | GST/QST Eligible
1 |  |  | 0 | Equal | 10% | 3 | Yes
2 | 1. LAND | Land Acquisition | 1600000 | Upfront | 0% | 0 | Yes
3 | 1. LAND | Notary and cadastre | 19808 | Upfront | 0% | 0 | Yes
4 | 1. LAND | Cadastral operation | 105360 | Upfront | 0% | 0 | Yes
5 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Adjustment for Bldgs 5 & 6 | 479320 | Front-loaded | 10% | 3 | Yes
6 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Trailer pad, Access road, Septic tank | 10900 | Front-loaded | 10% | 3 | Yes
7 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Credit - Reservoir change | 1946765 | Front-loaded | 10% | 3 | Yes
8 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Credit - Reservoir change | 0 | Front-loaded | 10% | 3 | Yes
9 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Campus Civil | 143113 | Front-loaded | 10% | 3 | Yes
10 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Campus Civil | 30493 | Front-loaded | 10% | 3 | Yes
11 | 2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & backfill - Extension - Mtee Ryan Civil | 375295 | Front-loaded | 10% | 3 | Yes
12 | 2. SITE SERVICING + LANDSCAPE |  | 165563 | Front-loaded | 10% | 3 | Yes
13 | 2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 475672 | Front-loaded | 10% | 3 | Yes
14 | 2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 23100 | Front-loaded | 10% | 3 | Yes
15 | 2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 2300 | Front-loaded | 10% | 3 | Yes
16 | 2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 25102 | Front-loaded | 10% | 3 | Yes
17 | 2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 47223 | Front-loaded | 10% | 3 | Yes
18 | 2. SITE SERVICING + LANDSCAPE | Landscaping:Excavation & Backfill - Landscaping | 1065794 | Front-loaded | 10% | 3 | Yes
19 | 2. SITE SERVICING + LANDSCAPE | Electrical services | 252500 | Front-loaded | 10% | 3 | Yes
20 | 2. SITE SERVICING + LANDSCAPE | Electrical charging stations | 124981 | Front-loaded | 10% | 3 | Yes
21 | 3. HARD COSTS | Admin and profit | 1577987 | Equal | 10% | 3 | Yes
22 | 3. HARD COSTS | Insurance and bonding:Insurance | 278718 | Equal | 10% | 3 | Yes
23 | 3. HARD COSTS |  | 140525 | Equal | 10% | 3 | Yes
24 | 3. HARD COSTS | Insurance and bonding:Wrap-up | 36465 | Equal | 10% | 3 | Yes
25 | 3. HARD COSTS | Insurance and bonding:Bris des Machines | 2585 | Equal | 10% | 3 | Yes
26 | 3. HARD COSTS | Insurance and bonding:L&M and Performance Bonds | 0 | Equal | 10% | 3 | Yes
27 | 3. HARD COSTS | General conditions:CoSS Agent | 236000 | Equal | 10% | 3 | Yes
28 | 3. HARD COSTS | General conditions:RSS Agent | 213500 | Equal | 10% | 3 | Yes
29 | 3. HARD COSTS | General conditions:Superintendent 1 | 303400 | Equal | 10% | 3 | Yes
30 | 3. HARD COSTS | General conditions:Superintendent 2 | 266400 | Equal | 10% | 3 | Yes
31 | 3. HARD COSTS | General conditions:Project Manager | 150750 | Equal | 10% | 3 | Yes
32 | 3. HARD COSTS | General conditions:Labourer | 230020 | Equal | 10% | 3 | Yes
33 | 3. HARD COSTS | General Conditions: Logding | 11000 | Equal | 10% | 3 | Yes
34 | 3. HARD COSTS | General conditions:Site fencing | 10780 | Equal | 10% | 3 | Yes
35 | 3. HARD COSTS | General Conditions: Printing | 8048 | Equal | 10% | 3 | Yes
36 | 3. HARD COSTS | General conditions:Scaffolding-Cranes-Nacelles | 242750 | Equal | 10% | 3 | Yes
37 | 3. HARD COSTS | General conditions:Tool rental | 0 | Equal | 10% | 3 | Yes
38 | 3. HARD COSTS | General conditions:Garbage chutes | 0 | Equal | 10% | 3 | Yes
39 | 3. HARD COSTS | General conditions:Garbage containers | 87875 | Equal | 10% | 3 | Yes
40 | 3. HARD COSTS | General conditions:Site trailers - Rental | 51500 | Equal | 10% | 3 | Yes
41 | 3. HARD COSTS | General conditions:Storage container rental | 8798 | Equal | 10% | 3 | Yes
42 | 3. HARD COSTS | General conditions:Sanitary trailer - Rental/Purchase - Portable Toilets | 56242 | Equal | 10% | 3 | Yes
43 | 3. HARD COSTS | General conditions:Winter conditions | 881840 | Equal | 10% | 3 | Yes
44 | 3. HARD COSTS | General conditions:Camera Security - Equipement | 29000 | Equal | 10% | 3 | Yes
45 | 3. HARD COSTS | General conditions:Camera Security - Monthly surveillance fees | 0 | Equal | 10% | 3 | Yes
46 | 3. HARD COSTS | General conditions:Temporary Electrical - Installation | 147967 | Equal | 10% | 3 | Yes
47 | 3. HARD COSTS | General conditions:Temporary Electrical - Consumption | 0 | Equal | 10% | 3 | Yes
48 | 3. HARD COSTS | General conditions:Trailer & WC maintenance | 6500 | Equal | 10% | 3 | Yes
49 | 3. HARD COSTS | General conditions:Daily cleaning | 60094 | Equal | 10% | 3 | Yes
50 | 3. HARD COSTS | General conditions:Final Cleaning | 53800 | Equal | 10% | 3 | Yes
51 | 3. HARD COSTS | General conditions:Laboratory & Testing | 98600 | Equal | 10% | 3 | Yes
52 | 3. HARD COSTS | General conditions:Surveyor | 35407 | Equal | 10% | 3 | Yes
53 | 3. HARD COSTS | General conditions:Project signage | 181830 | Equal | 10% | 3 | Yes
54 | 3. HARD COSTS |  | 6000 | Equal | 10% | 3 | Yes
55 | 3. HARD COSTS | General conditions:Miscellaneous | 1901 | Equal | 10% | 3 | Yes
56 | 3. HARD COSTS | Formwork:Concrete purchases - Hambro floors | 94276 | Front-loaded | 10% | 3 | Yes
57 | 3. HARD COSTS | Formwork:Stair slab concrete | 27681 | Front-loaded | 10% | 3 | Yes
58 | 3. HARD COSTS | Concrete:Concrete purchases | 97941 | Front-loaded | 10% | 3 | Yes
59 | 3. HARD COSTS | Formwork:Insulated formwork | 2681518 | Front-loaded | 10% | 3 | Yes
60 | 3. HARD COSTS |  | 0 | Equal | 10% | 3 | Yes
61 | 3. HARD COSTS | Formwork:Wire mesh - Hambro floors | 62581 | Front-loaded | 10% | 3 | Yes
62 | 3. HARD COSTS | Formwork:Cement finishing | 163654 | Front-loaded | 10% | 3 | Yes
63 | 3. HARD COSTS | Formwork:Stair slab cement finishing | 0 | Front-loaded | 10% | 3 | Yes
64 | 3. HARD COSTS | Formwork:Stair slab concrete pumps | 0 | Front-loaded | 10% | 3 | Yes
65 | 3. HARD COSTS | Formwork:Concrete pumps | 31715 | Front-loaded | 10% | 3 | Yes
66 | 3. HARD COSTS | Concrete:Concrete pumps | 0 | Front-loaded | 10% | 3 | Yes
67 | 3. HARD COSTS | Concrete:Concrete accessories | 79342 | Front-loaded | 10% | 3 | Yes
68 | 3. HARD COSTS | Concrete:Labour - Accessories | 0 | Front-loaded | 10% | 3 | Yes
69 | 3. HARD COSTS | Concrete:Polyethylene .006 - changed to .010 2024-01-22 | 0 | Front-loaded | 10% | 3 | Yes
70 | 3. HARD COSTS | Concrete:3'' Rigid insulation (4' perimeter) - changed to 2'' Blue | 0 | Front-loaded | 10% | 3 | Yes
71 | 3. HARD COSTS | Concrete:Labour - Rigid insulation | 0 | Front-loaded | 10% | 3 | Yes
72 | 3. HARD COSTS | Concrete:Wet cure | 0 | Front-loaded | 10% | 3 | Yes
73 | 3. HARD COSTS | Formwork:Hambro joists | 494189 | Front-loaded | 10% | 3 | Yes
74 | 3. HARD COSTS | Metal works:Stairs | 682129 | Equal | 10% | 3 | Yes
75 | 3. HARD COSTS | Metal works:Steel bases for balcony columns | 0 | Equal | 10% | 3 | Yes
76 | 3. HARD COSTS | Handrails:Railings | 116664 | Equal | 10% | 3 | Yes
77 | 3. HARD COSTS | Carpentry rough:Miscellaneous carpentry labour (DCL) | 754800 | Equal | 10% | 3 | Yes
78 | 3. HARD COSTS | Formwork:Roof trusses - Labour | 550190 | Front-loaded | 10% | 3 | Yes
79 | 3. HARD COSTS | Carpentry rough:Millwork & WC Acc. Blocking | 252570 | Equal | 10% | 3 | Yes
80 | 3. HARD COSTS | Carpentry rough:Stair rail blocking | 0 | Equal | 10% | 3 | Yes
81 | 3. HARD COSTS | Carpentry rough:OSB Dryguard - Roof | 0 | Mid-weighted | 10% | 3 | Yes
82 | 3. HARD COSTS | Carpentry rough:Materials - small roofs | 498625 | Equal | 10% | 3 | Yes
83 | 3. HARD COSTS | Formwork:Hambro plywood purchases | 0 | Front-loaded | 10% | 3 | Yes
84 | 3. HARD COSTS | Handrails:Balcony structures | 0 | Equal | 10% | 3 | Yes
85 | 3. HARD COSTS | Handrails:Floors | 114000 | Equal | 10% | 3 | Yes
86 | 3. HARD COSTS | Carpentry rough:Roof trusses | 176601 | Mid-weighted | 10% | 3 | Yes
87 | 3. HARD COSTS | Kitchen:Kitchens & vanities (QC) | 844652 | Back-loaded | 10% | 3 | Yes
88 | 3. HARD COSTS |  | 0 | Equal | 10% | 3 | Yes
89 | 3. HARD COSTS | Kitchen:Quartz counters - Purchase | 177900 | Back-loaded | 10% | 3 | Yes
90 | 3. HARD COSTS | Kitchen:Quartz counters - Installation | 0 | Back-loaded | 10% | 3 | Yes
91 | 3. HARD COSTS | Carpentry rough:Roof insulation | 35500 | Mid-weighted | 10% | 3 | Yes
92 | 3. HARD COSTS | Exterior finishes:Wood siding | 1482450 | Mid-weighted | 10% | 3 | Yes
93 | 3. HARD COSTS | Exterior finishes:Acrylic stucco & Duroc | 280000 | Mid-weighted | 10% | 3 | Yes
94 | 3. HARD COSTS | Roof, membrane:Roofing (Shingles) | 280825 | Mid-weighted | 10% | 3 | Yes
95 | 3. HARD COSTS | Roof, membrane:Roofing (Winter conditions) | 0 | Mid-weighted | 10% | 3 | Yes
96 | 3. HARD COSTS | Roof, membrane:Rain Gutters | 36000 | Mid-weighted | 10% | 3 | Yes
97 | 3. HARD COSTS | Fenestration:Caulking | 91200 | Mid-weighted | 10% | 3 | Yes
98 | 3. HARD COSTS | Doors and hardware:Wood doors | 449827 | Equal | 10% | 3 | Yes
99 | 3. HARD COSTS |  | 49800 | Equal | 10% | 3 | Yes
100 | 3. HARD COSTS |  | 157600 | Equal | 10% | 3 | Yes
101 | 3. HARD COSTS | Carpentry finish:Carpentry | 248100 | Equal | 10% | 3 | Yes
102 | 3. HARD COSTS | Doors and hardware:Baseboard, 1/4-round & casing | 108850 | Equal | 10% | 3 | Yes
103 | 3. HARD COSTS | Carpentry finish:Shelving & Finish materials | 0 | Equal | 10% | 3 | Yes
104 | 3. HARD COSTS | Fenestration:Windows & patio-doors - Supply | 851388 | Mid-weighted | 10% | 3 | Yes
105 | 3. HARD COSTS | Fenestration:Transport & Handling - Quebec | 0 | Mid-weighted | 10% | 3 | Yes
106 | 3. HARD COSTS | Interior systems:Drywall | 2345879 | Back-loaded | 10% | 3 | Yes
107 | 3. HARD COSTS | Ceramic:Ceramic Purchase, Transport, Handling & Installation | 179184 | Back-loaded | 10% | 3 | Yes
108 | 3. HARD COSTS | Ceramic:Shower walls | 0 | Back-loaded | 10% | 3 | Yes
109 | 3. HARD COSTS | Ceramic:Bathroom floors (SPC) | 208859 | Back-loaded | 10% | 3 | Yes
110 | 3. HARD COSTS | Floor covering:Vinyl flooring & Transport, Handling | 343300 | Back-loaded | 10% | 3 | Yes
111 | 3. HARD COSTS |  | 0 | Equal | 10% | 3 | Yes
112 | 3. HARD COSTS | Paint:Painting | 366000 | Back-loaded | 10% | 3 | Yes
113 | 3. HARD COSTS |  | 102000 | Equal | 10% | 3 | Yes
114 | 3. HARD COSTS |  | 0 | Equal | 10% | 3 | Yes
115 | 3. HARD COSTS | Railings:Foot grilles | 0 | Equal | 10% | 3 | Yes
116 | 3. HARD COSTS | Railings:Interior signage | 15300 | Back-loaded | 10% | 3 | Yes
117 | 3. HARD COSTS | Railings:WC acccessories | 25750 | Equal | 10% | 3 | Yes
118 | 3. HARD COSTS | Plumbing:Plumbing (Rough S/I; Finish I/O) | 1643900 | Mid-weighted | 10% | 3 | Yes
119 | 3. HARD COSTS | Plumbing:Plumbing finishes (S) - Toilet, Shower | 377966 | Mid-weighted | 10% | 3 | Yes
120 | 3. HARD COSTS | Fire protection:Extinguishers | 25500 | Equal | 10% | 3 | Yes
121 | 3. HARD COSTS | HVAC:HVAC | 790030 | Mid-weighted | 10% | 3 | Yes
122 | 3. HARD COSTS | Electricity:Electricity | 1866337 | Mid-weighted | 10% | 3 | Yes
123 | 3. HARD COSTS | Electricity:Lighting allowance | 53300 | Mid-weighted | 10% | 3 | Yes
124 | 3. HARD COSTS | Electricity:Transport & Handling - Quebec | 0 | Mid-weighted | 10% | 3 | Yes
125 | 3. HARD COSTS | Electricity:DEL Comptoirs (cuisines) | 0 | Mid-weighted | 10% | 3 | Yes
126 | 4. FF&E | Appliances | 403998 | Back-loaded | 5% | 3 | Yes
127 | 4. FF&E | Casegoods | 963770 | Back-loaded | 5% | 3 | Yes
128 | 4. FF&E | Smallwares | 250000 | Back-loaded | 5% | 3 | Yes
129 | 4. FF&E | Electronic Technology | 175000 | Back-loaded | 5% | 3 | Yes
130 | 5. PROFESSIONAL FEES | Accounting/bookkeeping | 49979 | Front-loaded | 10% | 3 | Yes
131 | 5. PROFESSIONAL FEES | Acoustical | 6740 | Front-loaded | 10% | 3 | Yes
132 | 5. PROFESSIONAL FEES | Appraisal/feasibility study | 67509 | Front-loaded | 10% | 3 | Yes
133 | 5. PROFESSIONAL FEES | Architect-design | 31063 | Front-loaded | 10% | 3 | Yes
134 | 5. PROFESSIONAL FEES | Architecture | 594877 | Front-loaded | 10% | 3 | Yes
135 | 5. PROFESSIONAL FEES | Development services fees | 1325000 | Front-loaded | 10% | 3 | Yes
136 | 5. PROFESSIONAL FEES | Engineer - civil | 227656 | Front-loaded | 10% | 3 | Yes
137 | 5. PROFESSIONAL FEES | Engineer - electrical | 0 | Front-loaded | 10% | 3 | Yes
138 | 5. PROFESSIONAL FEES | Engineer - geothermal | 0 | Front-loaded | 10% | 3 | Yes
139 | 5. PROFESSIONAL FEES | Engineer - mechanical | 89984 | Front-loaded | 10% | 3 | Yes
140 | 5. PROFESSIONAL FEES | Engineer - structural | 158013 | Front-loaded | 10% | 3 | Yes
141 | 5. PROFESSIONAL FEES | Environmental - Phases I/II | 17708 | Front-loaded | 10% | 3 | Yes
142 | 5. PROFESSIONAL FEES | Land survey, certificate of location | 5000 | Front-loaded | 10% | 3 | Yes
143 | 5. PROFESSIONAL FEES | Landscape architect | 81864 | Front-loaded | 10% | 3 | Yes
144 | 5. PROFESSIONAL FEES | Legal | 64523 | Front-loaded | 10% | 3 | Yes
145 | 5. PROFESSIONAL FEES | Marketing/leasing | 297679 | Front-loaded | 10% | 3 | Yes
146 | 5. PROFESSIONAL FEES | Quantity surveyor | 97080 | Front-loaded | 10% | 3 | Yes
147 | 5. PROFESSIONAL FEES | Soil/geotechnical/compaction | 93319 | Front-loaded | 10% | 3 | Yes
148 | 5. PROFESSIONAL FEES | Urban planner | 56552 | Front-loaded | 10% | 3 | Yes
149 | 5. PROFESSIONAL FEES | Water tests | 4000 | Front-loaded | 10% | 3 | Yes
150 | 5. PROFESSIONAL FEES | Declaration of co-ownership/shared services | 15000 | Front-loaded | 10% | 3 | Yes
151 | 6. FINANCE AND ADMINISTRATION | Carrying costs land | 240000 | Equal | 0% | 0 | Yes
152 | 6. FINANCE AND ADMINISTRATION | Construction interest | 1592483 | Equal | 0% | 0 | Yes
153 | 6. FINANCE AND ADMINISTRATION | Disbursements | 10220 | Equal | 0% | 0 | Yes
154 | 6. FINANCE AND ADMINISTRATION | Insurance | 44753 | Equal | 0% | 0 | Yes
155 | 6. FINANCE AND ADMINISTRATION | Legal fees | 125339 | Equal | 0% | 0 | Yes
156 | 6. FINANCE AND ADMINISTRATION | Lender fees | 112290 | Equal | 0% | 0 | Yes
157 | 6. FINANCE AND ADMINISTRATION | CMHC Insurance Premium | 452241 | Equal | 0% | 0 | Yes
158 | 6. FINANCE AND ADMINISTRATION | Mortage broker | 247344 | Equal | 0% | 0 | Yes
159 | 6. FINANCE AND ADMINISTRATION | Permits | 168546 | Equal | 0% | 0 | Yes
160 | 6. FINANCE AND ADMINISTRATION | Pre Construction Carrying costs | 273134 | Equal | 0% | 0 | Yes
161 | 6. FINANCE AND ADMINISTRATION | Taxes | 10000 | Equal | 0% | 0 | Yes
162 | 7. TAX ASSESSMENT | Self assesement taxes | 2087617 | At Completion | 0% | 0 | Yes
163 | 8. CONTINGENCY ALLOWANCE | Contingency | 500000 | As Needed | 0% | 0 | Yes
164 | 8. CONTINGENCY ALLOWANCE | Contingency Buy Down | 0 | As Needed | 0% | 0 | Yes
165 | 8. CONTINGENCY ALLOWANCE | Contingency Non-Classified | 0 | As Needed | 0% | 0 | Yes
166 | HOLDBACKS |  | 0 | Equal | 10% | 3 | Yes

## I_Unit Rent Roll Data
UNIT RENT ROLL DATA
Exact import from Units-Proforma_View_Tremb.csv
UnitId | UnitRentalTypes | Unit # | Planned Delivery Date for Occupancy | Projected Price Per Bedroom (from UnitRentalTypes) | Projected Rate | Bedroom Count (from UnitRentalTypes) | Units Operations ID
ADELE 1 A-101 | London | 101 |  |  | 1905 |  | ADELE -101 | 0
ADELE 1 A-201 | Berlin | 201 |  |  | 2455 |  | ADELE -201 | 0
ADELE 1 A-301 | Berlin | 301 |  |  | 2455 |  | ADELE -301
ADELE 1 A-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 1 A-202 | Berlin | 202 |  |  | 2455 |  | ADELE -202
ADELE 1 A-302 | Berlin | 302 |  |  | 2455 |  | ADELE -302
ADELE 1 B-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 1 B-201 | Paris | 201 |  |  | 1639 |  | ADELE -201
ADELE 1 B-202 | New York | 202 |  |  | 1589 |  | ADELE -202
ADELE 1 B-301 | Paris | 301 |  |  | 1639 |  | ADELE -301
ADELE 1 B-302 | New York | 302 |  |  | 1589 |  | ADELE -302
ADELE 1 B-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 1 B-202 | Paris | 202 |  |  | 1639 |  | ADELE -202
ADELE 1 B-203 | New York | 203 |  |  | 1589 |  | ADELE -203
ADELE 1 B-302 | Paris | 302 |  |  | 1639 |  | ADELE -302
ADELE 1 C-303 | New York | 303 |  |  | 1589 |  | ADELE -303
ADELE 1 C-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 1 C-201 | Berlin | 201 |  |  | 2455 |  | ADELE -201
ADELE 1 C-301 | Berlin | 301 |  |  | 2455 |  | ADELE -301
ADELE 1 C-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 2 D-303 | New York | 303 |  |  | 1589 |  | ADELE -303
ADELE 2 D-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 2 E-302 | Berlin | 302 |  |  | 2455 |  | ADELE -302
ADELE 2 D-301 | Berlin | 301 |  |  | 2455 |  | ADELE -301
ADELE 1 C-202 | Berlin | 202 |  |  | 2455 |  | ADELE -202
ADELE 2 E-203 | New York | 203 |  |  | 1589 |  | ADELE -203
ADELE 2 D-201 | Paris | 201 |  |  | 1639 |  | ADELE -201
ADELE 2 F-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 2 E-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 2 E-301 | Paris | 301 |  |  | 1639 |  | ADELE -301
ADELE 2 D-302 | Paris | 302 |  |  | 1639 |  | ADELE -302
ADELE 2 E-302 | New York | 302 |  |  | 1589 |  | ADELE -302
ADELE 2 D-202 | Paris | 202 |  |  | 1639 |  | ADELE -202
ADELE 2 D-202 | New York | 202 |  |  | 1589 |  | ADELE -202
ADELE 2 E-201 | Berlin | 201 |  |  | 2455 |  | ADELE -201
ADELE 2 D-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 2 F-201 | Berlin | 201 |  |  | 2455 |  | ADELE -201
ADELE 2 F-301 | Berlin | 301 |  |  | 2455 |  | ADELE -301
ADELE 2 F-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 2 F-202 | Paris | 202 |  |  | 1639 |  | ADELE -202
ADELE 2 F-203 | New York | 203 |  |  | 1589 |  | ADELE -203
ADELE 2 F-302 | Paris | 302 |  |  | 1639 |  | ADELE -302
ADELE 2 F-303 | New York | 303 |  |  | 1589 |  | ADELE -303
ADELE 3 G-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 3 G-201 | Paris | 201 |  |  | 1639 |  | ADELE -201
ADELE 3 G-202 | New York | 202 |  |  | 1589 |  | ADELE -202
ADELE 3 G-301 | Paris | 301 |  |  | 1639 |  | ADELE -301
ADELE 3 G-302 | New York | 302 |  |  | 1589 |  | ADELE -302
ADELE 3 G-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 3 G-202 | Berlin | 202 |  |  | 2455 |  | ADELE -202
ADELE 3 H-301 | Berlin | 301 |  |  | 2455 |  | ADELE -301
ADELE 3 H-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 3 H-201 | Berlin | 201 |  |  | 2455 |  | ADELE -201
ADELE 3 H-302 | Berlin | 302 |  |  | 2455 |  | ADELE -302
ADELE 3 H-102 | London | 102 |  |  | 1905 |  | ADELE -102
ADELE 3 H-202 | Paris | 202 |  |  | 1639 |  | ADELE -202
ADELE 3 H-203 | New York | 203 |  |  | 1589 |  | ADELE -203
ADELE 3 H-302 | Paris | 302 |  |  | 1639 |  | ADELE -302
ADELE 3 H-303 | New York | 303 |  |  | 1589 |  | ADELE -303
ADELE 3 H-101 | London | 101 |  |  | 1905 |  | ADELE -101
ADELE 3 H-201 | Paris | 201 |  |  | 1639 |  | ADELE -201
ADELE 3 H-301 | Paris | 301 |  |  | 1639 |  | ADELE -301
ADELE 3 H-202 | New York | 202 |  |  | 1589 |  | ADELE -202
ADELE 3 H-302 | New York | 302 |  |  | 1589 |  | ADELE -302

## i_Cap Table
CAPITALIZATION TABLE
Investor equity commitments and capital calls
INVESTOR COMMITMENTS
Investor Name | Class | Commitment Amount | % of Class | % of Total Equity
Vafkor | E | 750000 | 100% | 100%
Masteko Inc | E | 500000 | 40% | 40%
Gerome | A | 4.5 | 100% | 0.00036%
Julie Maranda Medicine Professional Corporation | A | 10.5 | 70% | 0.00084%
Masteko Inc (Additional) | E | 3152 | 0.2515% | 0.2515%
Michel Roux Holding Co | E | 250000 | 16.63% | 16.63%
Dr Éric Tardif C.P. Inc. | E | 250000 | 14.26% | 14.26%
Tristan Koran | E | 100000 | 5.396% | 5.396%
Additional Equity Required | E | 946848 | 33.82% | 33.82%
CLASS A SUBTOTAL (GP - Land Contribution) | A | 15 | 100.00% | 0.0005357%
CLASS E SUBTOTAL (LP Units) | E | 2800000 | 100.00% | 100%
TOTAL EQUITY COMMITMENTS |  | 2800015 |  | 100.00%
CAPITAL CALLS DURING CONSTRUCTION
Based on pro-rata share when Class E equity is called
Investor Name | Class | Commitment | % of Class E | Total Called | Remaining
Vafkor | E | 750000 | 26.79% | 750000 | 0
Masteko Inc | E | 500000 | 17.86% | 500000 | 0
Gerome | A | 4.5 | N/A - Class A | 4.5 | 0
Julie Maranda Medicine Professional Corporation | A | 10.5 | N/A - Class A | 10.5 | 0
Masteko Inc (Additional) | E | 3152 | 0.1126% | 3152 | 0
Michel Roux Holding Co | E | 250000 | 8.929% | 250000 | 0
Dr Éric Tardif C.P. Inc. | E | 250000 | 8.929% | 250000 | 0
Tristan Koran | E | 100000 | 3.571% | 100000 | 0
Additional Equity Required | E | 946848 | 33.82% | 946848 | 0
TOTAL CAPITAL CALLED |  | 2800015 |  | 2800015 | 0
NOTE: 'Total Called' is now editable (yellow cells)
• By default, Total Called = Commitment | 2800015
• Edit Total Called amounts as capital is actually called | 2800015
• Senior Construction Financing and other tabs reference these values | 2800015
Difference (Should be close to $0) | 0

## I_Preferred Equity
PREFERRED EQUITY TABLE
Subordinated Loan #1 - Preferred Equity investors
PREFERRED EQUITY INVESTORS
ID | Investor Name | Contribution Amount | Interest Rate | Notes
PE1 |  | 0 | 0%
PE2 |  | 0 | 0%
PE3 |  | 0 | 0%
PE4 |  | 0 | 0%
PE5 |  | 0 | 0%
PE6 | 0 | 0 | 0%
PE7 |  | 0 | 0%
PE8 |  | 0 | 0%
PE9 |  | 0 | 0%
PE10 |  | 0 | 0%
TOTAL | Preferred Equity | 0 | Weighted Avg: | #DIV/0!
INSTRUCTIONS:
• Enter investor names in column B (yellow cells)
• Enter contribution amounts in column C (yellow cells)
• Enter interest rates in column D (yellow cells)
• Add any notes in column E
• Total will update automatically
• This total is linked to Sources & Uses - Construction
0
0
0
0

## I_Mezzanine Debt
MEZZANINE DEBT TABLE
Subordinated Loan #2 - Mezzanine lenders
MEZZANINE LENDERS
ID | Lender Name | Loan Amount | Interest Rate | Notes
MEZZ1 |  | 0 | 0%
MEZZ2 |  | 0 | 0%
MEZZ3 |  | 0 | 0%
MEZZ4 |  | 0 | 0%
MEZZ5 |  | 0 | 0%
MEZZ6 |  | 0 | 0%
MEZZ7 |  | 0 | 0%
MEZZ8 |  | 0 | 0%
MEZZ9 |  | 0 | 0%
MEZZ10 |  | 0 | 0%
TOTAL | Mezzanine Debt | 0 | Weighted Avg: | #DIV/0!
INSTRUCTIONS:
• Enter lender names in column B (yellow cells)
• Enter loan amounts in column C (yellow cells)
• Enter interest rates in column D (yellow cells)
• Add any notes in column E
• Total will update automatically
• This total is linked to Sources & Uses - Construction

## Construction Budget & Draws
CONSTRUCTION BUDGET & DRAWS
References Budget Input Data tab
BUDGET SUMMARY BY CATEGORY
1. LAND | 1725168
2. SITE SERVICING + LANDSCAPE | 5168121
3. HARD COSTS | 25732155
4. FF&E | 1792768
5. PROFESSIONAL FEES | 3283546
6. FINANCE AND ADMINISTRATION | 3276350
7. TAX ASSESSMENT | 2087617
8. CONTINGENCY ALLOWANCE | 500000
TOTAL PROJECT COST (Before Cap Interest) | 43565725
Capitalized Interest (from Financing tabs) | 0
Construction interest | -1592483
GRAND TOTAL PROJECT COST | 43565725
MONTHLY DRAW SCHEDULE
Detailed monthly draws by line item
Phasing logic:
Category | Subcategory | Budget Amount | Planned Budget Amount | Checksum | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Month 18 | Month 19 | Month 20 | Month 21 | Month 22 | Month 23 | Month 24 | Month 25 | Month 26 | Month 27 | Month 28 | Month 29 | Month 30 | Month 31 | Month 32 | Month 33 | Month 34 | Month 35 | Month 36
1. LAND | Land Acquisition | 1600000 | 1600000 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. LAND | Notary and cadastre | 19808 | 19808 | 0 | 19808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. LAND | Cadastral operation | 105360 | 105360 | 0 | 105360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Adjustment for Bldgs 5 & 6 | 479320 | 471945.8462 | 7374.1538 | 44244.9231 | 44244.9231 | 44244.9231 | 44244.9231 | 44244.9231 | 44244.9231 | 29496.6154 | 29496.6154 | 29496.6154 | 29496.6154 | 29496.6154 | 29496.6154 | 29496.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Trailer pad, Access road, Septic tank | 10900 | 10732.3077 | 167.6923 | 1006.1538 | 1006.1538 | 1006.1538 | 1006.1538 | 1006.1538 | 1006.1538 | 670.7692 | 670.7692 | 670.7692 | 670.7692 | 670.7692 | 670.7692 | 670.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Credit - Reservoir change | 1946765 | 1916814.7692 | 29950.2308 | 179701.3846 | 179701.3846 | 179701.3846 | 179701.3846 | 179701.3846 | 179701.3846 | 119800.9231 | 119800.9231 | 119800.9231 | 119800.9231 | 119800.9231 | 119800.9231 | 119800.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Credit - Reservoir change | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Campus Civil | 143113 | 140911.2615 | 2201.7385 | 13210.4308 | 13210.4308 | 13210.4308 | 13210.4308 | 13210.4308 | 13210.4308 | 8806.9538 | 8806.9538 | 8806.9538 | 8806.9538 | 8806.9538 | 8806.9538 | 8806.9538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Campus Civil | 30493 | 30023.8769 | 469.1231 | 2814.7385 | 2814.7385 | 2814.7385 | 2814.7385 | 2814.7385 | 2814.7385 | 1876.4923 | 1876.4923 | 1876.4923 | 1876.4923 | 1876.4923 | 1876.4923 | 1876.4923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & backfill - Extension - Mtee Ryan Civil | 375295 | 369521.2308 | 5773.7692 | 34642.6154 | 34642.6154 | 34642.6154 | 34642.6154 | 34642.6154 | 34642.6154 | 23095.0769 | 23095.0769 | 23095.0769 | 23095.0769 | 23095.0769 | 23095.0769 | 23095.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | 0 | 165563 | 163015.8769 | 2547.1231 | 15282.7385 | 15282.7385 | 15282.7385 | 15282.7385 | 15282.7385 | 15282.7385 | 10188.4923 | 10188.4923 | 10188.4923 | 10188.4923 | 10188.4923 | 10188.4923 | 10188.4923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 475672 | 468353.9692 | 7318.0308 | 43908.1846 | 43908.1846 | 43908.1846 | 43908.1846 | 43908.1846 | 43908.1846 | 29272.1231 | 29272.1231 | 29272.1231 | 29272.1231 | 29272.1231 | 29272.1231 | 29272.1231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 23100 | 22744.6154 | 355.3846 | 2132.3077 | 2132.3077 | 2132.3077 | 2132.3077 | 2132.3077 | 2132.3077 | 1421.5385 | 1421.5385 | 1421.5385 | 1421.5385 | 1421.5385 | 1421.5385 | 1421.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 2300 | 2264.6154 | 35.3846 | 212.3077 | 212.3077 | 212.3077 | 212.3077 | 212.3077 | 212.3077 | 141.5385 | 141.5385 | 141.5385 | 141.5385 | 141.5385 | 141.5385 | 141.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 25102 | 24715.8154 | 386.1846 | 2317.1077 | 2317.1077 | 2317.1077 | 2317.1077 | 2317.1077 | 2317.1077 | 1544.7385 | 1544.7385 | 1544.7385 | 1544.7385 | 1544.7385 | 1544.7385 | 1544.7385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 47223 | 46496.4923 | 726.5077 | 4359.0462 | 4359.0462 | 4359.0462 | 4359.0462 | 4359.0462 | 4359.0462 | 2906.0308 | 2906.0308 | 2906.0308 | 2906.0308 | 2906.0308 | 2906.0308 | 2906.0308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Landscaping:Excavation & Backfill - Landscaping | 1065794 | 1049397.1692 | 16396.8308 | 98380.9846 | 98380.9846 | 98380.9846 | 98380.9846 | 98380.9846 | 98380.9846 | 65587.3231 | 65587.3231 | 65587.3231 | 65587.3231 | 65587.3231 | 65587.3231 | 65587.3231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Electrical services | 252500 | 248615.3846 | 3884.6154 | 23307.6923 | 23307.6923 | 23307.6923 | 23307.6923 | 23307.6923 | 23307.6923 | 15538.4615 | 15538.4615 | 15538.4615 | 15538.4615 | 15538.4615 | 15538.4615 | 15538.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Electrical charging stations | 124981 | 123058.2154 | 1922.7846 | 11536.7077 | 11536.7077 | 11536.7077 | 11536.7077 | 11536.7077 | 11536.7077 | 7691.1385 | 7691.1385 | 7691.1385 | 7691.1385 | 7691.1385 | 7691.1385 | 7691.1385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Admin and profit | 1577987 | 1577987 | 0 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Insurance and bonding:Insurance | 278718 | 278718 | 0 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | 0 | 140525 | 140525 | 0 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Insurance and bonding:Wrap-up | 36465 | 36465 | 0 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Insurance and bonding:Bris des Machines | 2585 | 2585 | 0 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Insurance and bonding:L&M and Performance Bonds | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:CoSS Agent | 236000 | 236000 | 0 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:RSS Agent | 213500 | 213500 | 0 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Superintendent 1 | 303400 | 303400 | 0 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Superintendent 2 | 266400 | 266400 | 0 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Project Manager | 150750 | 150750 | 0 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Labourer | 230020 | 230020 | 0 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General Conditions: Logding | 11000 | 11000 | 0 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Site fencing | 10780 | 10780 | 0 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General Conditions: Printing | 8048 | 8048 | 0 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Scaffolding-Cranes-Nacelles | 242750 | 242750 | 0 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Tool rental | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Garbage chutes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Garbage containers | 87875 | 87875 | 0 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Site trailers - Rental | 51500 | 51500 | 0 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Storage container rental | 8798 | 8798 | 0 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Sanitary trailer - Rental/Purchase - Portable Toilets | 56242 | 56242 | 0 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Winter conditions | 881840 | 881840 | 0 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Camera Security - Equipement | 29000 | 29000 | 0 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Camera Security - Monthly surveillance fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Temporary Electrical - Installation | 147967 | 147967 | 0 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Temporary Electrical - Consumption | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Trailer & WC maintenance | 6500 | 6500 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Daily cleaning | 60094 | 60094 | 0 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Final Cleaning | 53800 | 53800 | 0 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Laboratory & Testing | 98600 | 98600 | 0 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Surveyor | 35407 | 35407 | 0 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Project signage | 181830 | 181830 | 0 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | 0 | 6000 | 6000 | 0 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Miscellaneous | 1901 | 1901 | 0 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Concrete purchases - Hambro floors | 94276 | 92825.6 | 1450.4 | 8702.4 | 8702.4 | 8702.4 | 8702.4 | 8702.4 | 8702.4 | 5801.6 | 5801.6 | 5801.6 | 5801.6 | 5801.6 | 5801.6 | 5801.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Stair slab concrete | 27681 | 27255.1385 | 425.8615 | 2555.1692 | 2555.1692 | 2555.1692 | 2555.1692 | 2555.1692 | 2555.1692 | 1703.4462 | 1703.4462 | 1703.4462 | 1703.4462 | 1703.4462 | 1703.4462 | 1703.4462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Concrete purchases | 97941 | 96434.2154 | 1506.7846 | 9040.7077 | 9040.7077 | 9040.7077 | 9040.7077 | 9040.7077 | 9040.7077 | 6027.1385 | 6027.1385 | 6027.1385 | 6027.1385 | 6027.1385 | 6027.1385 | 6027.1385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Insulated formwork | 2681518 | 2640263.8769 | 41254.1231 | 247524.7385 | 247524.7385 | 247524.7385 | 247524.7385 | 247524.7385 | 247524.7385 | 165016.4923 | 165016.4923 | 165016.4923 | 165016.4923 | 165016.4923 | 165016.4923 | 165016.4923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Wire mesh - Hambro floors | 62581 | 61618.2154 | 962.7846 | 5776.7077 | 5776.7077 | 5776.7077 | 5776.7077 | 5776.7077 | 5776.7077 | 3851.1385 | 3851.1385 | 3851.1385 | 3851.1385 | 3851.1385 | 3851.1385 | 3851.1385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Cement finishing | 163654 | 161136.2462 | 2517.7538 | 15106.5231 | 15106.5231 | 15106.5231 | 15106.5231 | 15106.5231 | 15106.5231 | 10071.0154 | 10071.0154 | 10071.0154 | 10071.0154 | 10071.0154 | 10071.0154 | 10071.0154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Stair slab cement finishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Stair slab concrete pumps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Concrete pumps | 31715 | 31227.0769 | 487.9231 | 2927.5385 | 2927.5385 | 2927.5385 | 2927.5385 | 2927.5385 | 2927.5385 | 1951.6923 | 1951.6923 | 1951.6923 | 1951.6923 | 1951.6923 | 1951.6923 | 1951.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Concrete pumps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Concrete accessories | 79342 | 78121.3538 | 1220.6462 | 7323.8769 | 7323.8769 | 7323.8769 | 7323.8769 | 7323.8769 | 7323.8769 | 4882.5846 | 4882.5846 | 4882.5846 | 4882.5846 | 4882.5846 | 4882.5846 | 4882.5846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Labour - Accessories | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Polyethylene .006 - changed to .010 2024-01-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:3'' Rigid insulation (4' perimeter) - changed to 2'' Blue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Labour - Rigid insulation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Wet cure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Hambro joists | 494189 | 486586.0923 | 7602.9077 | 45617.4462 | 45617.4462 | 45617.4462 | 45617.4462 | 45617.4462 | 45617.4462 | 30411.6308 | 30411.6308 | 30411.6308 | 30411.6308 | 30411.6308 | 30411.6308 | 30411.6308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Metal works:Stairs | 682129 | 682129 | 0 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Metal works:Steel bases for balcony columns | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Handrails:Railings | 116664 | 116664 | 0 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Miscellaneous carpentry labour (DCL) | 754800 | 754800 | 0 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Roof trusses - Labour | 550190 | 541725.5385 | 8464.4615 | 50786.7692 | 50786.7692 | 50786.7692 | 50786.7692 | 50786.7692 | 50786.7692 | 33857.8462 | 33857.8462 | 33857.8462 | 33857.8462 | 33857.8462 | 33857.8462 | 33857.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Millwork & WC Acc. Blocking | 252570 | 252570 | 0 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Stair rail blocking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:OSB Dryguard - Roof | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Materials - small roofs | 498625 | 498625 | 0 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Hambro plywood purchases | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Handrails:Balcony structures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Handrails:Floors | 114000 | 114000 | 0 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Roof trusses | 176601 | 173884.0615 | 2716.9385 | 10867.7538 | 10867.7538 | 10867.7538 | 16301.6308 | 16301.6308 | 16301.6308 | 16301.6308 | 16301.6308 | 16301.6308 | 10867.7538 | 10867.7538 | 10867.7538 | 10867.7538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Kitchen:Kitchens & vanities (QC) | 844652 | 857646.6462 | -12994.6462 | 51978.5846 | 51978.5846 | 51978.5846 | 51978.5846 | 51978.5846 | 51978.5846 | 77967.8769 | 77967.8769 | 77967.8769 | 77967.8769 | 77967.8769 | 77967.8769 | 77967.8769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Kitchen:Quartz counters - Purchase | 177900 | 180636.9231 | -2736.9231 | 10947.6923 | 10947.6923 | 10947.6923 | 10947.6923 | 10947.6923 | 10947.6923 | 16421.5385 | 16421.5385 | 16421.5385 | 16421.5385 | 16421.5385 | 16421.5385 | 16421.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Kitchen:Quartz counters - Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Roof insulation | 35500 | 34953.8462 | 546.1538 | 2184.6154 | 2184.6154 | 2184.6154 | 3276.9231 | 3276.9231 | 3276.9231 | 3276.9231 | 3276.9231 | 3276.9231 | 2184.6154 | 2184.6154 | 2184.6154 | 2184.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Exterior finishes:Wood siding | 1482450 | 1459643.0769 | 22806.9231 | 91227.6923 | 91227.6923 | 91227.6923 | 136841.5385 | 136841.5385 | 136841.5385 | 136841.5385 | 136841.5385 | 136841.5385 | 91227.6923 | 91227.6923 | 91227.6923 | 91227.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Exterior finishes:Acrylic stucco & Duroc | 280000 | 275692.3077 | 4307.6923 | 17230.7692 | 17230.7692 | 17230.7692 | 25846.1538 | 25846.1538 | 25846.1538 | 25846.1538 | 25846.1538 | 25846.1538 | 17230.7692 | 17230.7692 | 17230.7692 | 17230.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Roof, membrane:Roofing (Shingles) | 280825 | 276504.6154 | 4320.3846 | 17281.5385 | 17281.5385 | 17281.5385 | 25922.3077 | 25922.3077 | 25922.3077 | 25922.3077 | 25922.3077 | 25922.3077 | 17281.5385 | 17281.5385 | 17281.5385 | 17281.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Roof, membrane:Roofing (Winter conditions) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Roof, membrane:Rain Gutters | 36000 | 35446.1538 | 553.8462 | 2215.3846 | 2215.3846 | 2215.3846 | 3323.0769 | 3323.0769 | 3323.0769 | 3323.0769 | 3323.0769 | 3323.0769 | 2215.3846 | 2215.3846 | 2215.3846 | 2215.3846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Fenestration:Caulking | 91200 | 89796.9231 | 1403.0769 | 5612.3077 | 5612.3077 | 5612.3077 | 8418.4615 | 8418.4615 | 8418.4615 | 8418.4615 | 8418.4615 | 8418.4615 | 5612.3077 | 5612.3077 | 5612.3077 | 5612.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Doors and hardware:Wood doors | 449827 | 449827 | 0 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | 0 | 49800 | 49800 | 0 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | 0 | 157600 | 157600 | 0 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry finish:Carpentry | 248100 | 248100 | 0 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Doors and hardware:Baseboard, 1/4-round & casing | 108850 | 108850 | 0 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry finish:Shelving & Finish materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Fenestration:Windows & patio-doors - Supply | 851388 | 838289.7231 | 13098.2769 | 52393.1077 | 52393.1077 | 52393.1077 | 78589.6615 | 78589.6615 | 78589.6615 | 78589.6615 | 78589.6615 | 78589.6615 | 52393.1077 | 52393.1077 | 52393.1077 | 52393.1077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Fenestration:Transport & Handling - Quebec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Interior systems:Drywall | 2345879 | 2381969.4462 | -36090.4462 | 144361.7846 | 144361.7846 | 144361.7846 | 144361.7846 | 144361.7846 | 144361.7846 | 216542.6769 | 216542.6769 | 216542.6769 | 216542.6769 | 216542.6769 | 216542.6769 | 216542.6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Ceramic:Ceramic Purchase, Transport, Handling & Installation | 179184 | 181940.6769 | -2756.6769 | 11026.7077 | 11026.7077 | 11026.7077 | 11026.7077 | 11026.7077 | 11026.7077 | 16540.0615 | 16540.0615 | 16540.0615 | 16540.0615 | 16540.0615 | 16540.0615 | 16540.0615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Ceramic:Shower walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Ceramic:Bathroom floors (SPC) | 208859 | 212072.2154 | -3213.2154 | 12852.8615 | 12852.8615 | 12852.8615 | 12852.8615 | 12852.8615 | 12852.8615 | 19279.2923 | 19279.2923 | 19279.2923 | 19279.2923 | 19279.2923 | 19279.2923 | 19279.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Floor covering:Vinyl flooring & Transport, Handling | 343300 | 348581.5385 | -5281.5385 | 21126.1538 | 21126.1538 | 21126.1538 | 21126.1538 | 21126.1538 | 21126.1538 | 31689.2308 | 31689.2308 | 31689.2308 | 31689.2308 | 31689.2308 | 31689.2308 | 31689.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Paint:Painting | 366000 | 371630.7692 | -5630.7692 | 22523.0769 | 22523.0769 | 22523.0769 | 22523.0769 | 22523.0769 | 22523.0769 | 33784.6154 | 33784.6154 | 33784.6154 | 33784.6154 | 33784.6154 | 33784.6154 | 33784.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | 0 | 102000 | 102000 | 0 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Railings:Foot grilles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Railings:Interior signage | 15300 | 15535.3846 | -235.3846 | 941.5385 | 941.5385 | 941.5385 | 941.5385 | 941.5385 | 941.5385 | 1412.3077 | 1412.3077 | 1412.3077 | 1412.3077 | 1412.3077 | 1412.3077 | 1412.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Railings:WC acccessories | 25750 | 25750 | 0 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Plumbing:Plumbing (Rough S/I; Finish I/O) | 1643900 | 1618609.2308 | 25290.7692 | 101163.0769 | 101163.0769 | 101163.0769 | 151744.6154 | 151744.6154 | 151744.6154 | 151744.6154 | 151744.6154 | 151744.6154 | 101163.0769 | 101163.0769 | 101163.0769 | 101163.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Plumbing:Plumbing finishes (S) - Toilet, Shower | 377966 | 372151.1385 | 5814.8615 | 23259.4462 | 23259.4462 | 23259.4462 | 34889.1692 | 34889.1692 | 34889.1692 | 34889.1692 | 34889.1692 | 34889.1692 | 23259.4462 | 23259.4462 | 23259.4462 | 23259.4462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Fire protection:Extinguishers | 25500 | 25500 | 0 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | HVAC:HVAC | 790030 | 777875.6923 | 12154.3077 | 48617.2308 | 48617.2308 | 48617.2308 | 72925.8462 | 72925.8462 | 72925.8462 | 72925.8462 | 72925.8462 | 72925.8462 | 48617.2308 | 48617.2308 | 48617.2308 | 48617.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Electricity:Electricity | 1866337 | 1837624.1231 | 28712.8769 | 114851.5077 | 114851.5077 | 114851.5077 | 172277.2615 | 172277.2615 | 172277.2615 | 172277.2615 | 172277.2615 | 172277.2615 | 114851.5077 | 114851.5077 | 114851.5077 | 114851.5077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Electricity:Lighting allowance | 53300 | 52480 | 820 | 3280 | 3280 | 3280 | 4920 | 4920 | 4920 | 4920 | 4920 | 4920 | 3280 | 3280 | 3280 | 3280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Electricity:Transport & Handling - Quebec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Electricity:DEL Comptoirs (cuisines) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. FF&E | Appliances | 403998 | 410213.3538 | -6215.3538 | 24861.4154 | 24861.4154 | 24861.4154 | 24861.4154 | 24861.4154 | 24861.4154 | 37292.1231 | 37292.1231 | 37292.1231 | 37292.1231 | 37292.1231 | 37292.1231 | 37292.1231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. FF&E | Casegoods | 963770 | 978597.2308 | -14827.2308 | 59308.9231 | 59308.9231 | 59308.9231 | 59308.9231 | 59308.9231 | 59308.9231 | 88963.3846 | 88963.3846 | 88963.3846 | 88963.3846 | 88963.3846 | 88963.3846 | 88963.3846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. FF&E | Smallwares | 250000 | 253846.1538 | -3846.1538 | 15384.6154 | 15384.6154 | 15384.6154 | 15384.6154 | 15384.6154 | 15384.6154 | 23076.9231 | 23076.9231 | 23076.9231 | 23076.9231 | 23076.9231 | 23076.9231 | 23076.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. FF&E | Electronic Technology | 175000 | 177692.3077 | -2692.3077 | 10769.2308 | 10769.2308 | 10769.2308 | 10769.2308 | 10769.2308 | 10769.2308 | 16153.8462 | 16153.8462 | 16153.8462 | 16153.8462 | 16153.8462 | 16153.8462 | 16153.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Accounting/bookkeeping | 49979 | 49210.0923 | 768.9077 | 4613.4462 | 4613.4462 | 4613.4462 | 4613.4462 | 4613.4462 | 4613.4462 | 3075.6308 | 3075.6308 | 3075.6308 | 3075.6308 | 3075.6308 | 3075.6308 | 3075.6308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Acoustical | 6740 | 6636.3077 | 103.6923 | 622.1538 | 622.1538 | 622.1538 | 622.1538 | 622.1538 | 622.1538 | 414.7692 | 414.7692 | 414.7692 | 414.7692 | 414.7692 | 414.7692 | 414.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Appraisal/feasibility study | 67509 | 66470.4 | 1038.6 | 6231.6 | 6231.6 | 6231.6 | 6231.6 | 6231.6 | 6231.6 | 4154.4 | 4154.4 | 4154.4 | 4154.4 | 4154.4 | 4154.4 | 4154.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Architect-design | 31063 | 30585.1077 | 477.8923 | 2867.3538 | 2867.3538 | 2867.3538 | 2867.3538 | 2867.3538 | 2867.3538 | 1911.5692 | 1911.5692 | 1911.5692 | 1911.5692 | 1911.5692 | 1911.5692 | 1911.5692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Architecture | 594877 | 585725.0462 | 9151.9538 | 54911.7231 | 54911.7231 | 54911.7231 | 54911.7231 | 54911.7231 | 54911.7231 | 36607.8154 | 36607.8154 | 36607.8154 | 36607.8154 | 36607.8154 | 36607.8154 | 36607.8154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Development services fees | 1325000 | 1304615.3846 | 20384.6154 | 122307.6923 | 122307.6923 | 122307.6923 | 122307.6923 | 122307.6923 | 122307.6923 | 81538.4615 | 81538.4615 | 81538.4615 | 81538.4615 | 81538.4615 | 81538.4615 | 81538.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Engineer - civil | 227656 | 224153.6 | 3502.4 | 21014.4 | 21014.4 | 21014.4 | 21014.4 | 21014.4 | 21014.4 | 14009.6 | 14009.6 | 14009.6 | 14009.6 | 14009.6 | 14009.6 | 14009.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Engineer - electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Engineer - geothermal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Engineer - mechanical | 89984 | 88599.6308 | 1384.3692 | 8306.2154 | 8306.2154 | 8306.2154 | 8306.2154 | 8306.2154 | 8306.2154 | 5537.4769 | 5537.4769 | 5537.4769 | 5537.4769 | 5537.4769 | 5537.4769 | 5537.4769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Engineer - structural | 158013 | 155582.0308 | 2430.9692 | 14585.8154 | 14585.8154 | 14585.8154 | 14585.8154 | 14585.8154 | 14585.8154 | 9723.8769 | 9723.8769 | 9723.8769 | 9723.8769 | 9723.8769 | 9723.8769 | 9723.8769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Environmental - Phases I/II | 17708 | 17435.5692 | 272.4308 | 1634.5846 | 1634.5846 | 1634.5846 | 1634.5846 | 1634.5846 | 1634.5846 | 1089.7231 | 1089.7231 | 1089.7231 | 1089.7231 | 1089.7231 | 1089.7231 | 1089.7231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Land survey, certificate of location | 5000 | 4923.0769 | 76.9231 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Landscape architect | 81864 | 80604.5538 | 1259.4462 | 7556.6769 | 7556.6769 | 7556.6769 | 7556.6769 | 7556.6769 | 7556.6769 | 5037.7846 | 5037.7846 | 5037.7846 | 5037.7846 | 5037.7846 | 5037.7846 | 5037.7846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Legal | 64523 | 63530.3385 | 992.6615 | 5955.9692 | 5955.9692 | 5955.9692 | 5955.9692 | 5955.9692 | 5955.9692 | 3970.6462 | 3970.6462 | 3970.6462 | 3970.6462 | 3970.6462 | 3970.6462 | 3970.6462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Marketing/leasing | 297679 | 293099.3231 | 4579.6769 | 27478.0615 | 27478.0615 | 27478.0615 | 27478.0615 | 27478.0615 | 27478.0615 | 18318.7077 | 18318.7077 | 18318.7077 | 18318.7077 | 18318.7077 | 18318.7077 | 18318.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Quantity surveyor | 97080 | 95586.4615 | 1493.5385 | 8961.2308 | 8961.2308 | 8961.2308 | 8961.2308 | 8961.2308 | 8961.2308 | 5974.1538 | 5974.1538 | 5974.1538 | 5974.1538 | 5974.1538 | 5974.1538 | 5974.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Soil/geotechnical/compaction | 93319 | 91883.3231 | 1435.6769 | 8614.0615 | 8614.0615 | 8614.0615 | 8614.0615 | 8614.0615 | 8614.0615 | 5742.7077 | 5742.7077 | 5742.7077 | 5742.7077 | 5742.7077 | 5742.7077 | 5742.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Urban planner | 56552 | 55681.9692 | 870.0308 | 5220.1846 | 5220.1846 | 5220.1846 | 5220.1846 | 5220.1846 | 5220.1846 | 3480.1231 | 3480.1231 | 3480.1231 | 3480.1231 | 3480.1231 | 3480.1231 | 3480.1231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Water tests | 4000 | 3938.4615 | 61.5385 | 369.2308 | 369.2308 | 369.2308 | 369.2308 | 369.2308 | 369.2308 | 246.1538 | 246.1538 | 246.1538 | 246.1538 | 246.1538 | 246.1538 | 246.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Declaration of co-ownership/shared services | 15000 | 14769.2308 | 230.7692 | 1384.6154 | 1384.6154 | 1384.6154 | 1384.6154 | 1384.6154 | 1384.6154 | 923.0769 | 923.0769 | 923.0769 | 923.0769 | 923.0769 | 923.0769 | 923.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Carrying costs land | 240000 | 240000 | 0 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Construction interest | 1592483 | 1592483 | 0 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Disbursements | 10220 | 10220 | 0 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Insurance | 44753 | 44753 | 0 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Legal fees | 125339 | 125339 | 0 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Lender fees | 112290 | 112290 | 0 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | CMHC Insurance Premium | 452241 | 452241 | 0 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Mortage broker | 247344 | 247344 | 0 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Permits | 168546 | 168546 | 0 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Pre Construction Carrying costs | 273134 | 273134 | 0 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Taxes | 10000 | 10000 | 0 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. TAX ASSESSMENT | Self assesement taxes | 2087617 | 2087617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2087617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. CONTINGENCY ALLOWANCE | Contingency | 500000 | 500000 | 0 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. CONTINGENCY ALLOWANCE | Contingency Buy Down | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. CONTINGENCY ALLOWANCE | Contingency Non-Classified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOLDBACKS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | All Line Items | 43565725 | 43343780.2462 | 221944.7538 | 4759939 | 3034771 | 3034771 | 3279863.2154 | 3279863.2154 | 3279863.2154 | 3081065.9231 | 3081065.9231 | 3081065.9231 | 2835973.7077 | 2835973.7077 | 2835973.7077 | 4923590.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONSTRUCTION PERIOD CASH FLOW
Professional CFO-grade tracking - Subordinated sources deployed BEFORE Senior Loan
Item | Description | Type | Total |  | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29
OPENING BALANCE | Cash at beginning of month | Balance | 0 |  | 0 | 5177402.8725 | 2142631.8725 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
CASH INFLOWS | Sources of cash
1. Class A Equity (Land) | From Sources & Uses - upfront | Input | 15 |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Class E Equity Calls | From Sources & Uses - as needed | Input | 2800015 |  | 2800015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Preferred Equity Draws | From Sources & Uses - as needed | Input | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Mezzanine Debt Draws | From Sources & Uses - as needed | Input | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. Required Additional Equity | Additional capital if needed | Input | 7137311.8725 |  | 7137311.8725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. SENIOR LOAN ADVANCE | Covers construction after subordinated | Calc | 33506438.3737 |  | 0 | 0 | 992139.1275 | 3279863.2154 | 3279863.2154 | 3279863.2154 | 3081065.9231 | 3081065.9231 | 3081065.9231 | 2835973.7077 | 2835973.7077 | 2835973.7077 | 4923590.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. Interdisbursement LOC Draw | Maintains $100k minimum (max $1M total) | Calc | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL INFLOWS | Sum of all sources |  | 43443780.2462 |  | 9937341.8725 | 0 | 992139.1275 | 3279863.2154 | 3279863.2154 | 3279863.2154 | 3081065.9231 | 3081065.9231 | 3081065.9231 | 2835973.7077 | 2835973.7077 | 2835973.7077 | 4923590.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CASH OUTFLOWS | Uses of cash
Construction Costs | From budget schedule (row 190) | Calc | 43343780.2462 |  | 4759939 | 3034771 | 3034771 | 3279863.2154 | 3279863.2154 | 3279863.2154 | 3081065.9231 | 3081065.9231 | 3081065.9231 | 2835973.7077 | 2835973.7077 | 2835973.7077 | 4923590.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest Payments | On LOC balances | Input | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interdisbursement LOC Repayments | Paydown of LOC | Input | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL OUTFLOWS | Sum of all uses |  | 43343780.2462 |  | 4759939 | 3034771 | 3034771 | 3279863.2154 | 3279863.2154 | 3279863.2154 | 3081065.9231 | 3081065.9231 | 3081065.9231 | 2835973.7077 | 2835973.7077 | 2835973.7077 | 4923590.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NET CASH FLOW | Inflows - Outflows |  | 100000 |  | 5177402.8725 | -3034771 | -2042631.8725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CLOSING BALANCE | Opening + Net Cash Flow |  | 100000 |  | 5177402.8725 | 2142631.8725 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
Cash vs $100k Minimum | Closing - $100,000 (should be ≥ $0) | Check | ≥ $0 is OK |  | 5077402.8725 | 2042631.8725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interdisbursement LOC Balance | Cumulative balance (should be ≤ $1M) | Check | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Sources Check | Cash Flow Total vs Sources & Uses | Check
| Senior Loan Advance Left |  |  |  | 33628383.1275 | 33628383.1275 | 32636244 | 29356380.7846 | 26076517.5692 | 22796654.3538 | 19715588.4308 | 16634522.5077 | 13553456.5846 | 10717482.8769 | 7881509.1692 | 5045535.4615 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538 | 121944.7538
BUSINESS RULES & VALIDATION
Automated checks to ensure model integrity
Check Description | Formula | Result | Status
1. Minimum Cash Balance ($100k) | All closing balances ≥ $100,000 | 0 | ✓ PASS
2. Senior Loan vs Maximum | Total drawn ≤ S&U maximum | -121944.7538 | ✓ PASS
3. Interdisbursement LOC Limit ($1M) | All LOC balances ≤ $1,000,000 | -1000000 | ✓ PASS
4. Total Sources Synchronization | Cash Flow total = S&U total | -121944.7538 | ✗ FAIL
OVERALL MODEL STATUS | All checks must pass | 3 | ⚠ ISSUES DETECTED ⚠
CHECKSUMS - SOURCES & USES RECONCILIATION
Verify all sources match between Cash Flow and Sources & Uses
Source Item | Cash Flow Total | Sources & Uses | Difference
Class A Equity | 15 | 15 | 0
Class E Equity | 2800015 | 2800015 | 0
Preferred Equity | 0 | 0 | 0
Mezzanine Debt | 0 | 0 | 0
Required Additional | 7137311.8725 | 7137311.8725 | 0
Senior Loan | 33506438.3737 | 33628383.1275 | -121944.7538
Interdisbursement LOC | 0 | N/A | N/A
TOTAL SOURCES | 43443780.2462 | 43565725 | -121944.7538
Status |  |  | ✗ NOT RECONCILED

## Sources & Uses - Construction
SOURCES & USES - CONSTRUCTION PERIOD
Static summary of construction funding
SOURCES OF FUNDS | Amount
In disbursement priority order (1→5)
1. Class A Equity (GP - Land Contribution) | 15 | Land contribution (upfront)
2. Class E Equity (LP Units) | 2800015 | From Cap Table - called during construction
3. Subordinated Loan #1 (Preferred Equity) | 0 | From Preferred Equity table
4. Subordinated Loan #2 (Mezzanine) | 0 | From Mezzanine Debt table
Required Additional Equity | 7137311.8725 | Calculated gap - additional equity needed
5. Senior Construction Loan | 33628383.1275 | Residual only - after all subordinated
TOTAL SOURCES | 43565725
USES OF FUNDS | Amount
1. LAND | 1725168
2. SITE SERVICING + LANDSCAPE | 5168121
3. HARD COSTS | 25732155
4. FF&E | 1792768
5. PROFESSIONAL FEES | 3283546
6. FINANCE AND ADMINISTRATION | 3276350
7. TAX ASSESSMENT | 2087617
8. CONTINGENCY ALLOWANCE | 500000
Capitalized Interest | 0
GST/QST Paid (Gross) | 0 | Set to $0
TOTAL USES | 43565725
RECONCILIATION
Total Sources | 43565725
Total Uses | 43565725
Difference (Should be $0) | 0
Status | ✓ BALANCED

## Senior Construction Financing
SENIOR CONSTRUCTION FINANCING
Monthly tracking of construction loan draws, interest, and equity calls
LOAN PARAMETERS
Loan-to-Cost (LTC): | 77.19%
Interest Rate (Annual): | 4.95%
Commitment Fee: | 0.1%
Total Project Cost (from Budget): | 43565725
Maximum Loan Amount (LTC × Cost): | 33628383.1275
MONTHLY CONSTRUCTION LOAN SCHEDULE
Month | Date | Phase | Beg Balance | Construction Draws | Less: Holdback (10%) | Net Draw | Senior Loan Advance | Interest Accrued | Commitment Fee | End Balance | Cumul Cap Interest | Equity Called (Class E) | Cash Balance Check
1 | 2025-03-31 | Construction | 0 | 4759939 | -475993.9 | 4283945.1 | 0 | 0 | 33628.3831 |  |  |  | #REF!
2 | 2025-04-30 | Construction | 0 | 3034771 | -303477.1 | 2731293.9 | 0 | 0 | 0 |  |  |  | -2731293.9
3 | 2025-05-31 | Construction | 0 | 3034771 | -303477.1 | 2731293.9 | 992139.1275 | 0 | 0 |  |  |  | -1739154.7725
4 | 2025-06-30 | Construction | 0 | 3279863.2154 | -327986.3215 | 2951876.8938 | 3279863.2154 | 0 | 0 |  |  |  | 327986.3215
5 | 2025-07-31 | Construction | 0 | 3279863.2154 | -327986.3215 | 2951876.8938 | 3279863.2154 | 0 | 0 |  |  |  | 327986.3215
6 | 2025-08-31 | Construction | 0 | 3279863.2154 | -327986.3215 | 2951876.8938 | 3279863.2154 | 0 | 0 |  |  |  | 327986.3215
7 | 2025-09-30 | Construction | 0 | 3081065.9231 | -308106.5923 | 2772959.3308 | 3081065.9231 | 0 | 0 |  |  |  | 308106.5923
8 | 2025-10-31 | Construction | 0 | 3081065.9231 | -308106.5923 | 2772959.3308 | 3081065.9231 | 0 | 0 |  |  |  | 308106.5923
9 | 2025-11-30 | Construction | 0 | 3081065.9231 | -308106.5923 | 2772959.3308 | 3081065.9231 | 0 | 0 |  |  |  | 308106.5923
10 | 2025-12-31 | Construction | 0 | 2835973.7077 | -283597.3708 | 2552376.3369 | 2835973.7077 | 0 | 0 |  |  |  | 283597.3708
11 | 2026-01-31 | Construction | 0 | 2835973.7077 | -283597.3708 | 2552376.3369 | 2835973.7077 | 0 | 0 |  |  |  | 283597.3708
12 | 2026-02-28 | Construction | 0 | 2835973.7077 | -283597.3708 | 2552376.3369 | 2835973.7077 | 0 | 0 |  |  |  | 283597.3708
13 | 2026-03-31 | Construction | 0 | 4923590.7077 | -492359.0708 | 4431231.6369 | 4923590.7077 | 0 | 0 |  |  |  | 492359.0708
14 | 2026-04-30 | Lease-Up | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
15 | 2026-05-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
16 | 2026-06-30 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
17 | 2026-07-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
18 | 2026-08-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
19 | 2026-09-30 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
20 | 2026-10-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
21 | 2026-11-30 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
22 | 2026-12-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
23 | 2027-01-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
24 | 2027-02-28 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
25 | 2027-03-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
26 | 2027-04-30 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
27 | 2027-05-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
28 | 2027-06-30 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
29 | 2027-07-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
30 | 2027-08-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
31 | 2027-09-30 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
32 | 2027-10-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
33 | 2027-11-30 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
34 | 2027-12-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
35 | 2028-01-31 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
36 | 2028-02-29 | Stabilized | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
CONSTRUCTION PERIOD SUMMARY | 43343780.2462
Total Construction Draws: | 43343780.2462
Total Holdback: | -4334378.0246
Total Senior Loan Advanced: | 33506438.3737
Total Capitalized Interest: | 0
Total Class E Equity Called: | 2800015
Senior Loan Balance at Refi: | 0

## Draw Calc (Hidden) (hidden)
DETAILED PHASING CALCULATION
Row alignment matches Budget Input Data exactly
Category | Subcategory | Mo 1 | Mo 2 | Mo 3 | Mo 4 | Mo 5 | Mo 6 | Mo 7 | Mo 8 | Mo 9 | Mo 10 | Mo 11 | Mo 12 | Mo 13 | Mo 14 | Mo 15 | Mo 16 | Mo 17 | Mo 18 | Mo 19 | Mo 20 | Mo 21 | Mo 22 | Mo 23 | Mo 24 | Mo 25 | Mo 26 | Mo 27 | Mo 28 | Mo 29 | Mo 30 | Mo 31 | Mo 32 | Mo 33 | Mo 34 | Mo 35 | Mo 36
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. LAND | Land Acquisition | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. LAND | Notary and cadastre | 19808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. LAND | Cadastral operation | 105360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Adjustment for Bldgs 5 & 6 | 44244.9231 | 44244.9231 | 44244.9231 | 44244.9231 | 44244.9231 | 44244.9231 | 29496.6154 | 29496.6154 | 29496.6154 | 29496.6154 | 29496.6154 | 29496.6154 | 29496.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Trailer pad, Access road, Septic tank | 1006.1538 | 1006.1538 | 1006.1538 | 1006.1538 | 1006.1538 | 1006.1538 | 670.7692 | 670.7692 | 670.7692 | 670.7692 | 670.7692 | 670.7692 | 670.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Credit - Reservoir change | 179701.3846 | 179701.3846 | 179701.3846 | 179701.3846 | 179701.3846 | 179701.3846 | 119800.9231 | 119800.9231 | 119800.9231 | 119800.9231 | 119800.9231 | 119800.9231 | 119800.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Credit - Reservoir change | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Campus Civil | 13210.4308 | 13210.4308 | 13210.4308 | 13210.4308 | 13210.4308 | 13210.4308 | 8806.9538 | 8806.9538 | 8806.9538 | 8806.9538 | 8806.9538 | 8806.9538 | 8806.9538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & Backfill - Campus Civil | 2814.7385 | 2814.7385 | 2814.7385 | 2814.7385 | 2814.7385 | 2814.7385 | 1876.4923 | 1876.4923 | 1876.4923 | 1876.4923 | 1876.4923 | 1876.4923 | 1876.4923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Extension of services:Excavation & backfill - Extension - Mtee Ryan Civil | 34642.6154 | 34642.6154 | 34642.6154 | 34642.6154 | 34642.6154 | 34642.6154 | 23095.0769 | 23095.0769 | 23095.0769 | 23095.0769 | 23095.0769 | 23095.0769 | 23095.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE |  | 15282.7385 | 15282.7385 | 15282.7385 | 15282.7385 | 15282.7385 | 15282.7385 | 10188.4923 | 10188.4923 | 10188.4923 | 10188.4923 | 10188.4923 | 10188.4923 | 10188.4923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 43908.1846 | 43908.1846 | 43908.1846 | 43908.1846 | 43908.1846 | 43908.1846 | 29272.1231 | 29272.1231 | 29272.1231 | 29272.1231 | 29272.1231 | 29272.1231 | 29272.1231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 2132.3077 | 2132.3077 | 2132.3077 | 2132.3077 | 2132.3077 | 2132.3077 | 1421.5385 | 1421.5385 | 1421.5385 | 1421.5385 | 1421.5385 | 1421.5385 | 1421.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 212.3077 | 212.3077 | 212.3077 | 212.3077 | 212.3077 | 212.3077 | 141.5385 | 141.5385 | 141.5385 | 141.5385 | 141.5385 | 141.5385 | 141.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 2317.1077 | 2317.1077 | 2317.1077 | 2317.1077 | 2317.1077 | 2317.1077 | 1544.7385 | 1544.7385 | 1544.7385 | 1544.7385 | 1544.7385 | 1544.7385 | 1544.7385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Onsite services - civil:Excavation & Backfill (PC) | 4359.0462 | 4359.0462 | 4359.0462 | 4359.0462 | 4359.0462 | 4359.0462 | 2906.0308 | 2906.0308 | 2906.0308 | 2906.0308 | 2906.0308 | 2906.0308 | 2906.0308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Landscaping:Excavation & Backfill - Landscaping | 98380.9846 | 98380.9846 | 98380.9846 | 98380.9846 | 98380.9846 | 98380.9846 | 65587.3231 | 65587.3231 | 65587.3231 | 65587.3231 | 65587.3231 | 65587.3231 | 65587.3231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Electrical services | 23307.6923 | 23307.6923 | 23307.6923 | 23307.6923 | 23307.6923 | 23307.6923 | 15538.4615 | 15538.4615 | 15538.4615 | 15538.4615 | 15538.4615 | 15538.4615 | 15538.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. SITE SERVICING + LANDSCAPE | Electrical charging stations | 11536.7077 | 11536.7077 | 11536.7077 | 11536.7077 | 11536.7077 | 11536.7077 | 7691.1385 | 7691.1385 | 7691.1385 | 7691.1385 | 7691.1385 | 7691.1385 | 7691.1385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Admin and profit | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 121383.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Insurance and bonding:Insurance | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 21439.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS |  | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 10809.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Insurance and bonding:Wrap-up | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 2805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Insurance and bonding:Bris des Machines | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 198.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Insurance and bonding:L&M and Performance Bonds | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:CoSS Agent | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 18153.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:RSS Agent | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 16423.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Superintendent 1 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 23338.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Superintendent 2 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 20492.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Project Manager | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 11596.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Labourer | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 17693.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General Conditions: Logding | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 846.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Site fencing | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 829.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General Conditions: Printing | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 619.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Scaffolding-Cranes-Nacelles | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 18673.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Tool rental | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Garbage chutes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Garbage containers | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 6759.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Site trailers - Rental | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 3961.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Storage container rental | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 676.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Sanitary trailer - Rental/Purchase - Portable Toilets | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 4326.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Winter conditions | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 67833.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Camera Security - Equipement | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 2230.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Camera Security - Monthly surveillance fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Temporary Electrical - Installation | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 11382.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Temporary Electrical - Consumption | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Trailer & WC maintenance | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Daily cleaning | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 4622.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Final Cleaning | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 4138.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Laboratory & Testing | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 7584.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Surveyor | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 2723.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Project signage | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 13986.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS |  | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | General conditions:Miscellaneous | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 146.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Concrete purchases - Hambro floors | 8702.4 | 8702.4 | 8702.4 | 8702.4 | 8702.4 | 8702.4 | 5801.6 | 5801.6 | 5801.6 | 5801.6 | 5801.6 | 5801.6 | 5801.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Stair slab concrete | 2555.1692 | 2555.1692 | 2555.1692 | 2555.1692 | 2555.1692 | 2555.1692 | 1703.4462 | 1703.4462 | 1703.4462 | 1703.4462 | 1703.4462 | 1703.4462 | 1703.4462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Concrete purchases | 9040.7077 | 9040.7077 | 9040.7077 | 9040.7077 | 9040.7077 | 9040.7077 | 6027.1385 | 6027.1385 | 6027.1385 | 6027.1385 | 6027.1385 | 6027.1385 | 6027.1385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Insulated formwork | 247524.7385 | 247524.7385 | 247524.7385 | 247524.7385 | 247524.7385 | 247524.7385 | 165016.4923 | 165016.4923 | 165016.4923 | 165016.4923 | 165016.4923 | 165016.4923 | 165016.4923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Wire mesh - Hambro floors | 5776.7077 | 5776.7077 | 5776.7077 | 5776.7077 | 5776.7077 | 5776.7077 | 3851.1385 | 3851.1385 | 3851.1385 | 3851.1385 | 3851.1385 | 3851.1385 | 3851.1385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Cement finishing | 15106.5231 | 15106.5231 | 15106.5231 | 15106.5231 | 15106.5231 | 15106.5231 | 10071.0154 | 10071.0154 | 10071.0154 | 10071.0154 | 10071.0154 | 10071.0154 | 10071.0154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Stair slab cement finishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Stair slab concrete pumps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Concrete pumps | 2927.5385 | 2927.5385 | 2927.5385 | 2927.5385 | 2927.5385 | 2927.5385 | 1951.6923 | 1951.6923 | 1951.6923 | 1951.6923 | 1951.6923 | 1951.6923 | 1951.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Concrete pumps | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Concrete accessories | 7323.8769 | 7323.8769 | 7323.8769 | 7323.8769 | 7323.8769 | 7323.8769 | 4882.5846 | 4882.5846 | 4882.5846 | 4882.5846 | 4882.5846 | 4882.5846 | 4882.5846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Labour - Accessories | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Polyethylene .006 - changed to .010 2024-01-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:3'' Rigid insulation (4' perimeter) - changed to 2'' Blue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Labour - Rigid insulation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Concrete:Wet cure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Hambro joists | 45617.4462 | 45617.4462 | 45617.4462 | 45617.4462 | 45617.4462 | 45617.4462 | 30411.6308 | 30411.6308 | 30411.6308 | 30411.6308 | 30411.6308 | 30411.6308 | 30411.6308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Metal works:Stairs | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 52471.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Metal works:Steel bases for balcony columns | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Handrails:Railings | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 8974.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Miscellaneous carpentry labour (DCL) | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 58061.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Roof trusses - Labour | 50786.7692 | 50786.7692 | 50786.7692 | 50786.7692 | 50786.7692 | 50786.7692 | 33857.8462 | 33857.8462 | 33857.8462 | 33857.8462 | 33857.8462 | 33857.8462 | 33857.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Millwork & WC Acc. Blocking | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 19428.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Stair rail blocking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:OSB Dryguard - Roof | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Materials - small roofs | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 38355.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Formwork:Hambro plywood purchases | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Handrails:Balcony structures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Handrails:Floors | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 8769.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Roof trusses | 10867.7538 | 10867.7538 | 10867.7538 | 16301.6308 | 16301.6308 | 16301.6308 | 16301.6308 | 16301.6308 | 16301.6308 | 10867.7538 | 10867.7538 | 10867.7538 | 10867.7538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Kitchen:Kitchens & vanities (QC) | 51978.5846 | 51978.5846 | 51978.5846 | 51978.5846 | 51978.5846 | 51978.5846 | 77967.8769 | 77967.8769 | 77967.8769 | 77967.8769 | 77967.8769 | 77967.8769 | 77967.8769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Kitchen:Quartz counters - Purchase | 10947.6923 | 10947.6923 | 10947.6923 | 10947.6923 | 10947.6923 | 10947.6923 | 16421.5385 | 16421.5385 | 16421.5385 | 16421.5385 | 16421.5385 | 16421.5385 | 16421.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Kitchen:Quartz counters - Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry rough:Roof insulation | 2184.6154 | 2184.6154 | 2184.6154 | 3276.9231 | 3276.9231 | 3276.9231 | 3276.9231 | 3276.9231 | 3276.9231 | 2184.6154 | 2184.6154 | 2184.6154 | 2184.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Exterior finishes:Wood siding | 91227.6923 | 91227.6923 | 91227.6923 | 136841.5385 | 136841.5385 | 136841.5385 | 136841.5385 | 136841.5385 | 136841.5385 | 91227.6923 | 91227.6923 | 91227.6923 | 91227.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Exterior finishes:Acrylic stucco & Duroc | 17230.7692 | 17230.7692 | 17230.7692 | 25846.1538 | 25846.1538 | 25846.1538 | 25846.1538 | 25846.1538 | 25846.1538 | 17230.7692 | 17230.7692 | 17230.7692 | 17230.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Roof, membrane:Roofing (Shingles) | 17281.5385 | 17281.5385 | 17281.5385 | 25922.3077 | 25922.3077 | 25922.3077 | 25922.3077 | 25922.3077 | 25922.3077 | 17281.5385 | 17281.5385 | 17281.5385 | 17281.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Roof, membrane:Roofing (Winter conditions) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Roof, membrane:Rain Gutters | 2215.3846 | 2215.3846 | 2215.3846 | 3323.0769 | 3323.0769 | 3323.0769 | 3323.0769 | 3323.0769 | 3323.0769 | 2215.3846 | 2215.3846 | 2215.3846 | 2215.3846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Fenestration:Caulking | 5612.3077 | 5612.3077 | 5612.3077 | 8418.4615 | 8418.4615 | 8418.4615 | 8418.4615 | 8418.4615 | 8418.4615 | 5612.3077 | 5612.3077 | 5612.3077 | 5612.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Doors and hardware:Wood doors | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 34602.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS |  | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 3830.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS |  | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 12123.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry finish:Carpentry | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 19084.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Doors and hardware:Baseboard, 1/4-round & casing | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 8373.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Carpentry finish:Shelving & Finish materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Fenestration:Windows & patio-doors - Supply | 52393.1077 | 52393.1077 | 52393.1077 | 78589.6615 | 78589.6615 | 78589.6615 | 78589.6615 | 78589.6615 | 78589.6615 | 52393.1077 | 52393.1077 | 52393.1077 | 52393.1077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Fenestration:Transport & Handling - Quebec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Interior systems:Drywall | 144361.7846 | 144361.7846 | 144361.7846 | 144361.7846 | 144361.7846 | 144361.7846 | 216542.6769 | 216542.6769 | 216542.6769 | 216542.6769 | 216542.6769 | 216542.6769 | 216542.6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Ceramic:Ceramic Purchase, Transport, Handling & Installation | 11026.7077 | 11026.7077 | 11026.7077 | 11026.7077 | 11026.7077 | 11026.7077 | 16540.0615 | 16540.0615 | 16540.0615 | 16540.0615 | 16540.0615 | 16540.0615 | 16540.0615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Ceramic:Shower walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Ceramic:Bathroom floors (SPC) | 12852.8615 | 12852.8615 | 12852.8615 | 12852.8615 | 12852.8615 | 12852.8615 | 19279.2923 | 19279.2923 | 19279.2923 | 19279.2923 | 19279.2923 | 19279.2923 | 19279.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Floor covering:Vinyl flooring & Transport, Handling | 21126.1538 | 21126.1538 | 21126.1538 | 21126.1538 | 21126.1538 | 21126.1538 | 31689.2308 | 31689.2308 | 31689.2308 | 31689.2308 | 31689.2308 | 31689.2308 | 31689.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Paint:Painting | 22523.0769 | 22523.0769 | 22523.0769 | 22523.0769 | 22523.0769 | 22523.0769 | 33784.6154 | 33784.6154 | 33784.6154 | 33784.6154 | 33784.6154 | 33784.6154 | 33784.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS |  | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 7846.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Railings:Foot grilles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Railings:Interior signage | 941.5385 | 941.5385 | 941.5385 | 941.5385 | 941.5385 | 941.5385 | 1412.3077 | 1412.3077 | 1412.3077 | 1412.3077 | 1412.3077 | 1412.3077 | 1412.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Railings:WC acccessories | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 1980.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Plumbing:Plumbing (Rough S/I; Finish I/O) | 101163.0769 | 101163.0769 | 101163.0769 | 151744.6154 | 151744.6154 | 151744.6154 | 151744.6154 | 151744.6154 | 151744.6154 | 101163.0769 | 101163.0769 | 101163.0769 | 101163.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Plumbing:Plumbing finishes (S) - Toilet, Shower | 23259.4462 | 23259.4462 | 23259.4462 | 34889.1692 | 34889.1692 | 34889.1692 | 34889.1692 | 34889.1692 | 34889.1692 | 23259.4462 | 23259.4462 | 23259.4462 | 23259.4462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Fire protection:Extinguishers | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 1961.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | HVAC:HVAC | 48617.2308 | 48617.2308 | 48617.2308 | 72925.8462 | 72925.8462 | 72925.8462 | 72925.8462 | 72925.8462 | 72925.8462 | 48617.2308 | 48617.2308 | 48617.2308 | 48617.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Electricity:Electricity | 114851.5077 | 114851.5077 | 114851.5077 | 172277.2615 | 172277.2615 | 172277.2615 | 172277.2615 | 172277.2615 | 172277.2615 | 114851.5077 | 114851.5077 | 114851.5077 | 114851.5077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Electricity:Lighting allowance | 3280 | 3280 | 3280 | 4920 | 4920 | 4920 | 4920 | 4920 | 4920 | 3280 | 3280 | 3280 | 3280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Electricity:Transport & Handling - Quebec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. HARD COSTS | Electricity:DEL Comptoirs (cuisines) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. FF&E | Appliances | 24861.4154 | 24861.4154 | 24861.4154 | 24861.4154 | 24861.4154 | 24861.4154 | 37292.1231 | 37292.1231 | 37292.1231 | 37292.1231 | 37292.1231 | 37292.1231 | 37292.1231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. FF&E | Casegoods | 59308.9231 | 59308.9231 | 59308.9231 | 59308.9231 | 59308.9231 | 59308.9231 | 88963.3846 | 88963.3846 | 88963.3846 | 88963.3846 | 88963.3846 | 88963.3846 | 88963.3846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. FF&E | Smallwares | 15384.6154 | 15384.6154 | 15384.6154 | 15384.6154 | 15384.6154 | 15384.6154 | 23076.9231 | 23076.9231 | 23076.9231 | 23076.9231 | 23076.9231 | 23076.9231 | 23076.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. FF&E | Electronic Technology | 10769.2308 | 10769.2308 | 10769.2308 | 10769.2308 | 10769.2308 | 10769.2308 | 16153.8462 | 16153.8462 | 16153.8462 | 16153.8462 | 16153.8462 | 16153.8462 | 16153.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Accounting/bookkeeping | 4613.4462 | 4613.4462 | 4613.4462 | 4613.4462 | 4613.4462 | 4613.4462 | 3075.6308 | 3075.6308 | 3075.6308 | 3075.6308 | 3075.6308 | 3075.6308 | 3075.6308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Acoustical | 622.1538 | 622.1538 | 622.1538 | 622.1538 | 622.1538 | 622.1538 | 414.7692 | 414.7692 | 414.7692 | 414.7692 | 414.7692 | 414.7692 | 414.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Appraisal/feasibility study | 6231.6 | 6231.6 | 6231.6 | 6231.6 | 6231.6 | 6231.6 | 4154.4 | 4154.4 | 4154.4 | 4154.4 | 4154.4 | 4154.4 | 4154.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Architect-design | 2867.3538 | 2867.3538 | 2867.3538 | 2867.3538 | 2867.3538 | 2867.3538 | 1911.5692 | 1911.5692 | 1911.5692 | 1911.5692 | 1911.5692 | 1911.5692 | 1911.5692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Architecture | 54911.7231 | 54911.7231 | 54911.7231 | 54911.7231 | 54911.7231 | 54911.7231 | 36607.8154 | 36607.8154 | 36607.8154 | 36607.8154 | 36607.8154 | 36607.8154 | 36607.8154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Development services fees | 122307.6923 | 122307.6923 | 122307.6923 | 122307.6923 | 122307.6923 | 122307.6923 | 81538.4615 | 81538.4615 | 81538.4615 | 81538.4615 | 81538.4615 | 81538.4615 | 81538.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Engineer - civil | 21014.4 | 21014.4 | 21014.4 | 21014.4 | 21014.4 | 21014.4 | 14009.6 | 14009.6 | 14009.6 | 14009.6 | 14009.6 | 14009.6 | 14009.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Engineer - electrical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Engineer - geothermal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Engineer - mechanical | 8306.2154 | 8306.2154 | 8306.2154 | 8306.2154 | 8306.2154 | 8306.2154 | 5537.4769 | 5537.4769 | 5537.4769 | 5537.4769 | 5537.4769 | 5537.4769 | 5537.4769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Engineer - structural | 14585.8154 | 14585.8154 | 14585.8154 | 14585.8154 | 14585.8154 | 14585.8154 | 9723.8769 | 9723.8769 | 9723.8769 | 9723.8769 | 9723.8769 | 9723.8769 | 9723.8769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Environmental - Phases I/II | 1634.5846 | 1634.5846 | 1634.5846 | 1634.5846 | 1634.5846 | 1634.5846 | 1089.7231 | 1089.7231 | 1089.7231 | 1089.7231 | 1089.7231 | 1089.7231 | 1089.7231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Land survey, certificate of location | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 461.5385 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Landscape architect | 7556.6769 | 7556.6769 | 7556.6769 | 7556.6769 | 7556.6769 | 7556.6769 | 5037.7846 | 5037.7846 | 5037.7846 | 5037.7846 | 5037.7846 | 5037.7846 | 5037.7846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Legal | 5955.9692 | 5955.9692 | 5955.9692 | 5955.9692 | 5955.9692 | 5955.9692 | 3970.6462 | 3970.6462 | 3970.6462 | 3970.6462 | 3970.6462 | 3970.6462 | 3970.6462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Marketing/leasing | 27478.0615 | 27478.0615 | 27478.0615 | 27478.0615 | 27478.0615 | 27478.0615 | 18318.7077 | 18318.7077 | 18318.7077 | 18318.7077 | 18318.7077 | 18318.7077 | 18318.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Quantity surveyor | 8961.2308 | 8961.2308 | 8961.2308 | 8961.2308 | 8961.2308 | 8961.2308 | 5974.1538 | 5974.1538 | 5974.1538 | 5974.1538 | 5974.1538 | 5974.1538 | 5974.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Soil/geotechnical/compaction | 8614.0615 | 8614.0615 | 8614.0615 | 8614.0615 | 8614.0615 | 8614.0615 | 5742.7077 | 5742.7077 | 5742.7077 | 5742.7077 | 5742.7077 | 5742.7077 | 5742.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Urban planner | 5220.1846 | 5220.1846 | 5220.1846 | 5220.1846 | 5220.1846 | 5220.1846 | 3480.1231 | 3480.1231 | 3480.1231 | 3480.1231 | 3480.1231 | 3480.1231 | 3480.1231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Water tests | 369.2308 | 369.2308 | 369.2308 | 369.2308 | 369.2308 | 369.2308 | 246.1538 | 246.1538 | 246.1538 | 246.1538 | 246.1538 | 246.1538 | 246.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. PROFESSIONAL FEES | Declaration of co-ownership/shared services | 1384.6154 | 1384.6154 | 1384.6154 | 1384.6154 | 1384.6154 | 1384.6154 | 923.0769 | 923.0769 | 923.0769 | 923.0769 | 923.0769 | 923.0769 | 923.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Carrying costs land | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 18461.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Construction interest | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 122498.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Disbursements | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 786.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Insurance | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 3442.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Legal fees | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 9641.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Lender fees | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 8637.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | CMHC Insurance Premium | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 34787.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Mortage broker | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 19026.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Permits | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 12965.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Pre Construction Carrying costs | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 21010.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. FINANCE AND ADMINISTRATION | Taxes | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 769.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. TAX ASSESSMENT | Self assesement taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2087617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. CONTINGENCY ALLOWANCE | Contingency | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 38461.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. CONTINGENCY ALLOWANCE | Contingency Buy Down | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. CONTINGENCY ALLOWANCE | Contingency Non-Classified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOLDBACKS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Time Axis
TIME AXIS
All dates and phases driven from Inputs & Assumptions tab
Month # | Date | Phase | Days in Month | Construction Mo | Permanent Mo | Year
1 | 2025-03-31 | Construction | 31 | 1 |  | 2025
2 | 2025-04-30 | Construction | 30 | 2 |  | 2025
3 | 2025-05-31 | Construction | 31 | 3 |  | 2025
4 | 2025-06-30 | Construction | 30 | 4 |  | 2025
5 | 2025-07-31 | Construction | 31 | 5 |  | 2025
6 | 2025-08-31 | Construction | 31 | 6 |  | 2025
7 | 2025-09-30 | Construction | 30 | 7 |  | 2025
8 | 2025-10-31 | Construction | 31 | 8 |  | 2025
9 | 2025-11-30 | Construction | 30 | 9 |  | 2025
10 | 2025-12-31 | Construction | 31 | 10 |  | 2025
11 | 2026-01-31 | Construction | 31 | 11 |  | 2026
12 | 2026-02-28 | Construction | 28 | 12 |  | 2026
13 | 2026-03-31 | Construction | 31 | 13 |  | 2026
14 | 2026-04-30 | Lease-Up | 30 |  |  | 2026
15 | 2026-05-31 | Stabilized | 31 |  | 1 | 2026
16 | 2026-06-30 | Stabilized | 30 |  | 2 | 2026
17 | 2026-07-31 | Stabilized | 31 |  | 3 | 2026
18 | 2026-08-31 | Stabilized | 31 |  | 4 | 2026
19 | 2026-09-30 | Stabilized | 30 |  | 5 | 2026
20 | 2026-10-31 | Stabilized | 31 |  | 6 | 2026
21 | 2026-11-30 | Stabilized | 30 |  | 7 | 2026
22 | 2026-12-31 | Stabilized | 31 |  | 8 | 2026
23 | 2027-01-31 | Stabilized | 31 |  | 9 | 2027
24 | 2027-02-28 | Stabilized | 28 |  | 10 | 2027
25 | 2027-03-31 | Stabilized | 31 |  | 11 | 2027
26 | 2027-04-30 | Stabilized | 30 |  | 12 | 2027
27 | 2027-05-31 | Stabilized | 31 |  | 13 | 2027
28 | 2027-06-30 | Stabilized | 30 |  | 14 | 2027
29 | 2027-07-31 | Stabilized | 31 |  | 15 | 2027
30 | 2027-08-31 | Stabilized | 31 |  | 16 | 2027
31 | 2027-09-30 | Stabilized | 30 |  | 17 | 2027
32 | 2027-10-31 | Stabilized | 31 |  | 18 | 2027
33 | 2027-11-30 | Stabilized | 30 |  | 19 | 2027
34 | 2027-12-31 | Stabilized | 31 |  | 20 | 2027
35 | 2028-01-31 | Stabilized | 31 |  | 21 | 2028
36 | 2028-02-29 | Stabilized | 29 |  | 22 | 2028
37 | 2028-03-31 | Stabilized | 31 |  | 23 | 2028
38 | 2028-04-30 | Stabilized | 30 |  | 24 | 2028
39 | 2028-05-31 | Stabilized | 31 |  | 25 | 2028
40 | 2028-06-30 | Stabilized | 30 |  | 26 | 2028
41 | 2028-07-31 | Stabilized | 31 |  | 27 | 2028
42 | 2028-08-31 | Stabilized | 31 |  | 28 | 2028
43 | 2028-09-30 | Stabilized | 30 |  | 29 | 2028
44 | 2028-10-31 | Stabilized | 31 |  | 30 | 2028
45 | 2028-11-30 | Stabilized | 30 |  | 31 | 2028
46 | 2028-12-31 | Stabilized | 31 |  | 32 | 2028
47 | 2029-01-31 | Stabilized | 31 |  | 33 | 2029
48 | 2029-02-28 | Stabilized | 28 |  | 34 | 2029
49 | 2029-03-31 | Stabilized | 31 |  | 35 | 2029
50 | 2029-04-30 | Stabilized | 30 |  | 36 | 2029
51 | 2029-05-31 | Stabilized | 31 |  | 37 | 2029
52 | 2029-06-30 | Stabilized | 30 |  | 38 | 2029
53 | 2029-07-31 | Stabilized | 31 |  | 39 | 2029
54 | 2029-08-31 | Stabilized | 31 |  | 40 | 2029
55 | 2029-09-30 | Stabilized | 30 |  | 41 | 2029
56 | 2029-10-31 | Stabilized | 31 |  | 42 | 2029
57 | 2029-11-30 | Stabilized | 30 |  | 43 | 2029
58 | 2029-12-31 | Stabilized | 31 |  | 44 | 2029
59 | 2030-01-31 | Stabilized | 31 |  | 45 | 2030
60 | 2030-02-28 | Stabilized | 28 |  | 46 | 2030
61 | 2030-03-31 | Stabilized | 31 |  | 47 | 2030
62 | 2030-04-30 | Stabilized | 30 |  | 48 | 2030
63 | 2030-05-31 | Stabilized | 31 |  | 49 | 2030
64 | 2030-06-30 | Stabilized | 30 |  | 50 | 2030
65 | 2030-07-31 | Stabilized | 31 |  | 51 | 2030
66 | 2030-08-31 | Stabilized | 31 |  | 52 | 2030
67 | 2030-09-30 | Stabilized | 30 |  | 53 | 2030
68 | 2030-10-31 | Stabilized | 31 |  | 54 | 2030
69 | 2030-11-30 | Stabilized | 30 |  | 55 | 2030
70 | 2030-12-31 | Stabilized | 31 |  | 56 | 2030
71 | 2031-01-31 | Stabilized | 31 |  | 57 | 2031
72 | 2031-02-28 | Stabilized | 28 |  | 58 | 2031
73 | 2031-03-31 | Stabilized | 31 |  | 59 | 2031
74 | 2031-04-30 | Stabilized | 30 |  | 60 | 2031
75 | 2031-05-31 | Exit | 31 |  |  | 2031
76 | 2031-06-30 | Exit | 30 |  |  | 2031
77 | 2031-07-31 | Exit | 31 |  |  | 2031
78 | 2031-08-31 | Exit | 31 |  |  | 2031
79 | 2031-09-30 | Exit | 30 |  |  | 2031
80 | 2031-10-31 | Exit | 31 |  |  | 2031
81 | 2031-11-30 | Exit | 30 |  |  | 2031
82 | 2031-12-31 | Exit | 31 |  |  | 2031
83 | 2032-01-31 | Exit | 31 |  |  | 2032
84 | 2032-02-29 | Exit | 29 |  |  | 2032
85 | 2032-03-31 | Exit | 31 |  |  | 2032
86 | 2032-04-30 | Exit | 30 |  |  | 2032
87 | 2032-05-31 | Exit | 31 |  |  | 2032
88 | 2032-06-30 | Exit | 30 |  |  | 2032
89 | 2032-07-31 | Exit | 31 |  |  | 2032
90 | 2032-08-31 | Exit | 31 |  |  | 2032
91 | 2032-09-30 | Exit | 30 |  |  | 2032
92 | 2032-10-31 | Exit | 31 |  |  | 2032
93 | 2032-11-30 | Exit | 30 |  |  | 2032
94 | 2032-12-31 | Exit | 31 |  |  | 2032
95 | 2033-01-31 | Exit | 31 |  |  | 2033
96 | 2033-02-28 | Exit | 28 |  |  | 2033
97 | 2033-03-31 | Exit | 31 |  |  | 2033
98 | 2033-04-30 | Exit | 30 |  |  | 2033
99 | 2033-05-31 | Exit | 31 |  |  | 2033
100 | 2033-06-30 | Exit | 30 |  |  | 2033
101 | 2033-07-31 | Exit | 31 |  |  | 2033
102 | 2033-08-31 | Exit | 31 |  |  | 2033
103 | 2033-09-30 | Exit | 30 |  |  | 2033
104 | 2033-10-31 | Exit | 31 |  |  | 2033
105 | 2033-11-30 | Exit | 30 |  |  | 2033
106 | 2033-12-31 | Exit | 31 |  |  | 2033
107 | 2034-01-31 | Exit | 31 |  |  | 2034
108 | 2034-02-28 | Exit | 28 |  |  | 2034
109 | 2034-03-31 | Exit | 31 |  |  | 2034
110 | 2034-04-30 | Exit | 30 |  |  | 2034
111 | 2034-05-31 | Exit | 31 |  |  | 2034
112 | 2034-06-30 | Exit | 30 |  |  | 2034
113 | 2034-07-31 | Exit | 31 |  |  | 2034
114 | 2034-08-31 | Exit | 31 |  |  | 2034
115 | 2034-09-30 | Exit | 30 |  |  | 2034
116 | 2034-10-31 | Exit | 31 |  |  | 2034
117 | 2034-11-30 | Exit | 30 |  |  | 2034
118 | 2034-12-31 | Exit | 31 |  |  | 2034
119 | 2035-01-31 | Exit | 31 |  |  | 2035
120 | 2035-02-28 | Exit | 28 |  |  | 2035

## OPEX
OPERATING BUDGET - POST CONSTRUCTION
Campus Adele
RENTAL REVENUE | Annual Amount | Escalation % | Notes
Number of Units | 64 |  | From Unit Rent Roll Data
Total Monthly Rent | 121408 |  | Sum of unit rents (Col F)
Annual Rental Revenue | 1456896 | 2% | Growth rate from I&A
SERVICE REVENUE
Internet | 38400 | 1.5% | 50 $/unit/mo
Reserved Parking | 42300 | 1.5% | 47 spaces @ $75/mo
EV Charging Stations | 22800 | 1.5% | 50 stations @ $38/mo
Total Service Revenue | 103500
GROSS POTENTIAL REVENUE | 1560396
Vacancy & Bad Debt Allowance | -93623.76 | 6%
EFFECTIVE GROSS INCOME (EGI) | 1466772.24
OPERATING EXPENSES | Annual Amount | Escalation % | Source
Assessed Property Value | 15000000 |  | Manual input - update to municipal assessment
Municipal Taxes | 112500 | 0% | 0.750% mill rate
School Taxes | 23400 | 0% | 0.1560% mill rate
Insurance | 16989 | 1% | From I&A
Repairs & Maintenance | 38400 | 1% | From I&A
Outdoor Amenities Maintenance | 2000 | 1% | From I&A
Snow Removal, Grass, Garbage | 23000 | 1% | From I&A
Janitor | 23000 | 1% | From I&A
Cleaning Reserve on Turnover | 7650 | 1% | From I&A
Security & Monitoring | 9000 | 1% | From I&A
Internet Expense | 20000 | 1% | From I&A
EV Charging Expense | 5000 | 1% | From I&A
Electricity (Common) | 12200 | 1% | From I&A
Administration (% of EGI) | 44003.1672 | 0% | 3.0% of EGI
Appliance & Furniture Reserve | 44800 | 1% | 700 $/unit/year
Structural Reserve (% of EGI) | 11000.7918 | 1% | 0.8% of EGI
TOTAL OPERATING EXPENSES | 392942.959
NET OPERATING INCOME (NOI) | 1073829.281
PROPERTY VALUATION & PERMANENT FINANCING
Exit Cap Rate | 4.5%
Implied Property Value | 23862872.9111
Loan-to-Value (LTV) - Check | 79.62% |  | Computed: Loan / Property Value
Permanent Loan Amount | 19000000 |  | Fixed amount from I&A
Total Interest Rate | 3.74%
Amortization (years) | 50
Monthly Payment | 70043.4603
Annual Debt Service | 840521.5236
DSCR | 1.2776
DSCR Covenant Minimum | 1.1
DSCR Test | PASS

## Permanent Financing
PERMANENT FINANCING - AMORTIZATION SCHEDULE
Loan Parameters
Loan Amount | 19000000
Interest Rate | 3.74%
Monthly Rate | 0.3117%
Amortization | 50 | years
Amort Periods | 600
Loan Term | 60 | months
Monthly Pmt | 70043.4603
Month | Date | Opening Bal. | Payment | Interest | Principal | Closing Bal.
26 | 2027-04-30 | 19000000 | 70043.4603 | 59216.6667 | 10826.7936 | 18989173.2064
27 | 2027-05-31 | 18989173.2064 | 70043.4603 | 59182.9232 | 10860.5371 | 18978312.6692
28 | 2027-06-30 | 18978312.6692 | 70043.4603 | 59149.0745 | 10894.3858 | 18967418.2834
29 | 2027-07-31 | 18967418.2834 | 70043.4603 | 59115.1203 | 10928.34 | 18956489.9434
30 | 2027-08-31 | 18956489.9434 | 70043.4603 | 59081.0603 | 10962.4 | 18945527.5435
31 | 2027-09-30 | 18945527.5435 | 70043.4603 | 59046.8942 | 10996.5661 | 18934530.9774
32 | 2027-10-31 | 18934530.9774 | 70043.4603 | 59012.6215 | 11030.8387 | 18923500.1386
33 | 2027-11-30 | 18923500.1386 | 70043.4603 | 58978.2421 | 11065.2182 | 18912434.9204
34 | 2027-12-31 | 18912434.9204 | 70043.4603 | 58943.7555 | 11099.7048 | 18901335.2156
35 | 2028-01-31 | 18901335.2156 | 70043.4603 | 58909.1614 | 11134.2989 | 18890200.9167
36 | 2028-02-29 | 18890200.9167 | 70043.4603 | 58874.4595 | 11169.0008 | 18879031.916
37 | 2028-03-31 | 18879031.916 | 70043.4603 | 58839.6495 | 11203.8108 | 18867828.1051
38 | 2028-04-30 | 18867828.1051 | 70043.4603 | 58804.7309 | 11238.7294 | 18856589.3758
39 | 2028-05-31 | 18856589.3758 | 70043.4603 | 58769.7036 | 11273.7567 | 18845315.619
40 | 2028-06-30 | 18845315.619 | 70043.4603 | 58734.567 | 11308.8933 | 18834006.7257
41 | 2028-07-31 | 18834006.7257 | 70043.4603 | 58699.321 | 11344.1393 | 18822662.5864
42 | 2028-08-31 | 18822662.5864 | 70043.4603 | 58663.9651 | 11379.4952 | 18811283.0912
43 | 2028-09-30 | 18811283.0912 | 70043.4603 | 58628.499 | 11414.9613 | 18799868.1299
44 | 2028-10-31 | 18799868.1299 | 70043.4603 | 58592.9223 | 11450.538 | 18788417.5919
45 | 2028-11-30 | 18788417.5919 | 70043.4603 | 58557.2348 | 11486.2255 | 18776931.3664
46 | 2028-12-31 | 18776931.3664 | 70043.4603 | 58521.4361 | 11522.0242 | 18765409.3422
47 | 2029-01-31 | 18765409.3422 | 70043.4603 | 58485.5258 | 11557.9345 | 18753851.4077
48 | 2029-02-28 | 18753851.4077 | 70043.4603 | 58449.5036 | 11593.9567 | 18742257.451
49 | 2029-03-31 | 18742257.451 | 70043.4603 | 58413.3691 | 11630.0912 | 18730627.3597
50 | 2029-04-30 | 18730627.3597 | 70043.4603 | 58377.1219 | 11666.3384 | 18718961.0214
51 | 2029-05-31 | 18718961.0214 | 70043.4603 | 58340.7618 | 11702.6984 | 18707258.3229
52 | 2029-06-30 | 18707258.3229 | 70043.4603 | 58304.2884 | 11739.1719 | 18695519.1511
53 | 2029-07-31 | 18695519.1511 | 70043.4603 | 58267.7014 | 11775.7589 | 18683743.3921
54 | 2029-08-31 | 18683743.3921 | 70043.4603 | 58231.0002 | 11812.4601 | 18671930.9321
55 | 2029-09-30 | 18671930.9321 | 70043.4603 | 58194.1847 | 11849.2756 | 18660081.6565
56 | 2029-10-31 | 18660081.6565 | 70043.4603 | 58157.2545 | 11886.2058 | 18648195.4507
57 | 2029-11-30 | 18648195.4507 | 70043.4603 | 58120.2092 | 11923.2511 | 18636272.1996
58 | 2029-12-31 | 18636272.1996 | 70043.4603 | 58083.0484 | 11960.4119 | 18624311.7876
59 | 2030-01-31 | 18624311.7876 | 70043.4603 | 58045.7717 | 11997.6886 | 18612314.0991
60 | 2030-02-28 | 18612314.0991 | 70043.4603 | 58008.3789 | 12035.0814 | 18600279.0177
61 | 2030-03-31 | 18600279.0177 | 70043.4603 | 57970.8696 | 12072.5907 | 18588206.427
62 | 2030-04-30 | 18588206.427 | 70043.4603 | 57933.2434 | 12110.2169 | 18576096.2101
63 | 2030-05-31 | 18576096.2101 | 70043.4603 | 57895.4999 | 12147.9604 | 18563948.2497
64 | 2030-06-30 | 18563948.2497 | 70043.4603 | 57857.6387 | 12185.8216 | 18551762.4281
65 | 2030-07-31 | 18551762.4281 | 70043.4603 | 57819.6596 | 12223.8007 | 18539538.6273
66 | 2030-08-31 | 18539538.6273 | 70043.4603 | 57781.5621 | 12261.8982 | 18527276.7291
67 | 2030-09-30 | 18527276.7291 | 70043.4603 | 57743.3458 | 12300.1145 | 18514976.6146
68 | 2030-10-31 | 18514976.6146 | 70043.4603 | 57705.0104 | 12338.4498 | 18502638.1648
69 | 2030-11-30 | 18502638.1648 | 70043.4603 | 57666.5556 | 12376.9047 | 18490261.2601
70 | 2030-12-31 | 18490261.2601 | 70043.4603 | 57627.9809 | 12415.4794 | 18477845.7807
71 | 2031-01-31 | 18477845.7807 | 70043.4603 | 57589.286 | 12454.1743 | 18465391.6064
72 | 2031-02-28 | 18465391.6064 | 70043.4603 | 57550.4705 | 12492.9898 | 18452898.6166
73 | 2031-03-31 | 18452898.6166 | 70043.4603 | 57511.534 | 12531.9263 | 18440366.6904
74 | 2031-04-30 | 18440366.6904 | 70043.4603 | 57472.4762 | 12570.9841 | 18427795.7063
75 | 2031-05-31 | 18427795.7063 | 70043.4603 | 57433.2966 | 12610.1637 | 18415185.5426
76 | 2031-06-30 | 18415185.5426 | 70043.4603 | 57393.9949 | 12649.4654 | 18402536.0772
77 | 2031-07-31 | 18402536.0772 | 70043.4603 | 57354.5708 | 12688.8895 | 18389847.1877
78 | 2031-08-31 | 18389847.1877 | 70043.4603 | 57315.0237 | 12728.4366 | 18377118.7511
79 | 2031-09-30 | 18377118.7511 | 70043.4603 | 57275.3534 | 12768.1069 | 18364350.6443
80 | 2031-10-31 | 18364350.6443 | 70043.4603 | 57235.5595 | 12807.9008 | 18351542.7435
81 | 2031-11-30 | 18351542.7435 | 70043.4603 | 57195.6416 | 12847.8187 | 18338694.9248
82 | 2031-12-31 | 18338694.9248 | 70043.4603 | 57155.5992 | 12887.8611 | 18325807.0636
83 | 2032-01-31 | 18325807.0636 | 70043.4603 | 57115.432 | 12928.0283 | 18312879.0354
84 | 2032-02-29 | 18312879.0354 | 70043.4603 | 57075.1397 | 12968.3206 | 18299910.7147
85 | 2032-03-31 | 18299910.7147 | 70043.4603 | 57034.7217 | 13008.7386 | 18286901.9762
TOTAL |  |  | 4202607.6178 | 3489509.5939 | 713098.0238
Balance at Maturity | [5 empty] | 18286901.9762

## Operating Proforma
MORGAN SAINTE-ADELE
OPERATING PROFORMA - MONTHLY CASH FLOW
Month # | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86
Date | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29 | 2028-03-31 | 2028-04-30 | 2028-05-31 | 2028-06-30 | 2028-07-31 | 2028-08-31 | 2028-09-30 | 2028-10-31 | 2028-11-30 | 2028-12-31 | 2029-01-31 | 2029-02-28 | 2029-03-31 | 2029-04-30 | 2029-05-31 | 2029-06-30 | 2029-07-31 | 2029-08-31 | 2029-09-30 | 2029-10-31 | 2029-11-30 | 2029-12-31 | 2030-01-31 | 2030-02-28 | 2030-03-31 | 2030-04-30 | 2030-05-31 | 2030-06-30 | 2030-07-31 | 2030-08-31 | 2030-09-30 | 2030-10-31 | 2030-11-30 | 2030-12-31 | 2031-01-31 | 2031-02-28 | 2031-03-31 | 2031-04-30 | 2031-05-31 | 2031-06-30 | 2031-07-31 | 2031-08-31 | 2031-09-30 | 2031-10-31 | 2031-11-30 | 2031-12-31 | 2032-01-31 | 2032-02-29 | 2032-03-31 | 2032-04-30
Phase | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Stabilized | Exit | Exit | Exit | Exit | Exit | Exit | Exit | Exit | Exit | Exit | Exit | Exit
Operating Year | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7
REVENUE
Gross Rental Income | 121408 | 123836.16 | 123836.16 | 123836.16 | 123836.16 | 123836.16 | 123836.16 | 123836.16 | 123836.16 | 123836.16 | 123836.16 | 123836.16 | 123836.16 | 126312.8832 | 126312.8832 | 126312.8832 | 126312.8832 | 126312.8832 | 126312.8832 | 126312.8832 | 126312.8832 | 126312.8832 | 126312.8832 | 126312.8832 | 126312.8832 | 128839.1409 | 128839.1409 | 128839.1409 | 128839.1409 | 128839.1409 | 128839.1409 | 128839.1409 | 128839.1409 | 128839.1409 | 128839.1409 | 128839.1409 | 128839.1409 | 131415.9237 | 131415.9237 | 131415.9237 | 131415.9237 | 131415.9237 | 131415.9237 | 131415.9237 | 131415.9237 | 131415.9237 | 131415.9237 | 131415.9237 | 131415.9237 | 134044.2422 | 134044.2422 | 134044.2422 | 134044.2422 | 134044.2422 | 134044.2422 | 134044.2422 | 134044.2422 | 134044.2422 | 134044.2422 | 134044.2422 | 134044.2422 | 136725.127
Internet Revenue | 3200 | 3248 | 3248 | 3248 | 3248 | 3248 | 3248 | 3248 | 3248 | 3248 | 3248 | 3248 | 3248 | 3296.72 | 3296.72 | 3296.72 | 3296.72 | 3296.72 | 3296.72 | 3296.72 | 3296.72 | 3296.72 | 3296.72 | 3296.72 | 3296.72 | 3346.1708 | 3346.1708 | 3346.1708 | 3346.1708 | 3346.1708 | 3346.1708 | 3346.1708 | 3346.1708 | 3346.1708 | 3346.1708 | 3346.1708 | 3346.1708 | 3396.3634 | 3396.3634 | 3396.3634 | 3396.3634 | 3396.3634 | 3396.3634 | 3396.3634 | 3396.3634 | 3396.3634 | 3396.3634 | 3396.3634 | 3396.3634 | 3447.3088 | 3447.3088 | 3447.3088 | 3447.3088 | 3447.3088 | 3447.3088 | 3447.3088 | 3447.3088 | 3447.3088 | 3447.3088 | 3447.3088 | 3447.3088 | 3499.0184
Parking Revenue | 3525 | 3577.875 | 3577.875 | 3577.875 | 3577.875 | 3577.875 | 3577.875 | 3577.875 | 3577.875 | 3577.875 | 3577.875 | 3577.875 | 3577.875 | 3631.5431 | 3631.5431 | 3631.5431 | 3631.5431 | 3631.5431 | 3631.5431 | 3631.5431 | 3631.5431 | 3631.5431 | 3631.5431 | 3631.5431 | 3631.5431 | 3686.0163 | 3686.0163 | 3686.0163 | 3686.0163 | 3686.0163 | 3686.0163 | 3686.0163 | 3686.0163 | 3686.0163 | 3686.0163 | 3686.0163 | 3686.0163 | 3741.3065 | 3741.3065 | 3741.3065 | 3741.3065 | 3741.3065 | 3741.3065 | 3741.3065 | 3741.3065 | 3741.3065 | 3741.3065 | 3741.3065 | 3741.3065 | 3797.4261 | 3797.4261 | 3797.4261 | 3797.4261 | 3797.4261 | 3797.4261 | 3797.4261 | 3797.4261 | 3797.4261 | 3797.4261 | 3797.4261 | 3797.4261 | 3854.3875
EV Charging Revenue | 1900 | 1928.5 | 1928.5 | 1928.5 | 1928.5 | 1928.5 | 1928.5 | 1928.5 | 1928.5 | 1928.5 | 1928.5 | 1928.5 | 1928.5 | 1957.4275 | 1957.4275 | 1957.4275 | 1957.4275 | 1957.4275 | 1957.4275 | 1957.4275 | 1957.4275 | 1957.4275 | 1957.4275 | 1957.4275 | 1957.4275 | 1986.7889 | 1986.7889 | 1986.7889 | 1986.7889 | 1986.7889 | 1986.7889 | 1986.7889 | 1986.7889 | 1986.7889 | 1986.7889 | 1986.7889 | 1986.7889 | 2016.5907 | 2016.5907 | 2016.5907 | 2016.5907 | 2016.5907 | 2016.5907 | 2016.5907 | 2016.5907 | 2016.5907 | 2016.5907 | 2016.5907 | 2016.5907 | 2046.8396 | 2046.8396 | 2046.8396 | 2046.8396 | 2046.8396 | 2046.8396 | 2046.8396 | 2046.8396 | 2046.8396 | 2046.8396 | 2046.8396 | 2046.8396 | 2077.5422
Total Service Revenue | 8625 | 8754.375 | 8754.375 | 8754.375 | 8754.375 | 8754.375 | 8754.375 | 8754.375 | 8754.375 | 8754.375 | 8754.375 | 8754.375 | 8754.375 | 8885.6906 | 8885.6906 | 8885.6906 | 8885.6906 | 8885.6906 | 8885.6906 | 8885.6906 | 8885.6906 | 8885.6906 | 8885.6906 | 8885.6906 | 8885.6906 | 9018.976 | 9018.976 | 9018.976 | 9018.976 | 9018.976 | 9018.976 | 9018.976 | 9018.976 | 9018.976 | 9018.976 | 9018.976 | 9018.976 | 9154.2606 | 9154.2606 | 9154.2606 | 9154.2606 | 9154.2606 | 9154.2606 | 9154.2606 | 9154.2606 | 9154.2606 | 9154.2606 | 9154.2606 | 9154.2606 | 9291.5745 | 9291.5745 | 9291.5745 | 9291.5745 | 9291.5745 | 9291.5745 | 9291.5745 | 9291.5745 | 9291.5745 | 9291.5745 | 9291.5745 | 9291.5745 | 9430.9482
GROSS POTENTIAL REVENUE | 130033 | 132590.535 | 132590.535 | 132590.535 | 132590.535 | 132590.535 | 132590.535 | 132590.535 | 132590.535 | 132590.535 | 132590.535 | 132590.535 | 132590.535 | 135198.5738 | 135198.5738 | 135198.5738 | 135198.5738 | 135198.5738 | 135198.5738 | 135198.5738 | 135198.5738 | 135198.5738 | 135198.5738 | 135198.5738 | 135198.5738 | 137858.1168 | 137858.1168 | 137858.1168 | 137858.1168 | 137858.1168 | 137858.1168 | 137858.1168 | 137858.1168 | 137858.1168 | 137858.1168 | 137858.1168 | 137858.1168 | 140570.1843 | 140570.1843 | 140570.1843 | 140570.1843 | 140570.1843 | 140570.1843 | 140570.1843 | 140570.1843 | 140570.1843 | 140570.1843 | 140570.1843 | 140570.1843 | 143335.8167 | 143335.8167 | 143335.8167 | 143335.8167 | 143335.8167 | 143335.8167 | 143335.8167 | 143335.8167 | 143335.8167 | 143335.8167 | 143335.8167 | 143335.8167 | 146156.0751
Vacancy & Bad Debt | -7801.98 | -7955.4321 | -7955.4321 | -7955.4321 | -7955.4321 | -7955.4321 | -7955.4321 | -7955.4321 | -7955.4321 | -7955.4321 | -7955.4321 | -7955.4321 | -7955.4321 | -8111.9144 | -8111.9144 | -8111.9144 | -8111.9144 | -8111.9144 | -8111.9144 | -8111.9144 | -8111.9144 | -8111.9144 | -8111.9144 | -8111.9144 | -8111.9144 | -8271.487 | -8271.487 | -8271.487 | -8271.487 | -8271.487 | -8271.487 | -8271.487 | -8271.487 | -8271.487 | -8271.487 | -8271.487 | -8271.487 | -8434.2111 | -8434.2111 | -8434.2111 | -8434.2111 | -8434.2111 | -8434.2111 | -8434.2111 | -8434.2111 | -8434.2111 | -8434.2111 | -8434.2111 | -8434.2111 | -8600.149 | -8600.149 | -8600.149 | -8600.149 | -8600.149 | -8600.149 | -8600.149 | -8600.149 | -8600.149 | -8600.149 | -8600.149 | -8600.149 | -8769.3645
EFFECTIVE GROSS INCOME | 122231.02 | 124635.1029 | 124635.1029 | 124635.1029 | 124635.1029 | 124635.1029 | 124635.1029 | 124635.1029 | 124635.1029 | 124635.1029 | 124635.1029 | 124635.1029 | 124635.1029 | 127086.6594 | 127086.6594 | 127086.6594 | 127086.6594 | 127086.6594 | 127086.6594 | 127086.6594 | 127086.6594 | 127086.6594 | 127086.6594 | 127086.6594 | 127086.6594 | 129586.6298 | 129586.6298 | 129586.6298 | 129586.6298 | 129586.6298 | 129586.6298 | 129586.6298 | 129586.6298 | 129586.6298 | 129586.6298 | 129586.6298 | 129586.6298 | 132135.9732 | 132135.9732 | 132135.9732 | 132135.9732 | 132135.9732 | 132135.9732 | 132135.9732 | 132135.9732 | 132135.9732 | 132135.9732 | 132135.9732 | 132135.9732 | 134735.6677 | 134735.6677 | 134735.6677 | 134735.6677 | 134735.6677 | 134735.6677 | 134735.6677 | 134735.6677 | 134735.6677 | 134735.6677 | 134735.6677 | 134735.6677 | 137386.7106
OPERATING EXPENSES
Municipal Taxes | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375 | 9375
School Taxes | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950 | 1950
Insurance | 1415.75 | 1429.9075 | 1429.9075 | 1429.9075 | 1429.9075 | 1429.9075 | 1429.9075 | 1429.9075 | 1429.9075 | 1429.9075 | 1429.9075 | 1429.9075 | 1429.9075 | 1444.2066 | 1444.2066 | 1444.2066 | 1444.2066 | 1444.2066 | 1444.2066 | 1444.2066 | 1444.2066 | 1444.2066 | 1444.2066 | 1444.2066 | 1444.2066 | 1458.6486 | 1458.6486 | 1458.6486 | 1458.6486 | 1458.6486 | 1458.6486 | 1458.6486 | 1458.6486 | 1458.6486 | 1458.6486 | 1458.6486 | 1458.6486 | 1473.2351 | 1473.2351 | 1473.2351 | 1473.2351 | 1473.2351 | 1473.2351 | 1473.2351 | 1473.2351 | 1473.2351 | 1473.2351 | 1473.2351 | 1473.2351 | 1487.9675 | 1487.9675 | 1487.9675 | 1487.9675 | 1487.9675 | 1487.9675 | 1487.9675 | 1487.9675 | 1487.9675 | 1487.9675 | 1487.9675 | 1487.9675 | 1502.8472
Repairs & Maintenance | 3200 | 3232 | 3232 | 3232 | 3232 | 3232 | 3232 | 3232 | 3232 | 3232 | 3232 | 3232 | 3232 | 3264.32 | 3264.32 | 3264.32 | 3264.32 | 3264.32 | 3264.32 | 3264.32 | 3264.32 | 3264.32 | 3264.32 | 3264.32 | 3264.32 | 3296.9632 | 3296.9632 | 3296.9632 | 3296.9632 | 3296.9632 | 3296.9632 | 3296.9632 | 3296.9632 | 3296.9632 | 3296.9632 | 3296.9632 | 3296.9632 | 3329.9328 | 3329.9328 | 3329.9328 | 3329.9328 | 3329.9328 | 3329.9328 | 3329.9328 | 3329.9328 | 3329.9328 | 3329.9328 | 3329.9328 | 3329.9328 | 3363.2322 | 3363.2322 | 3363.2322 | 3363.2322 | 3363.2322 | 3363.2322 | 3363.2322 | 3363.2322 | 3363.2322 | 3363.2322 | 3363.2322 | 3363.2322 | 3396.8645
Outdoor Amenities Maintenance | 166.6667 | 168.3333 | 168.3333 | 168.3333 | 168.3333 | 168.3333 | 168.3333 | 168.3333 | 168.3333 | 168.3333 | 168.3333 | 168.3333 | 168.3333 | 170.0167 | 170.0167 | 170.0167 | 170.0167 | 170.0167 | 170.0167 | 170.0167 | 170.0167 | 170.0167 | 170.0167 | 170.0167 | 170.0167 | 171.7168 | 171.7168 | 171.7168 | 171.7168 | 171.7168 | 171.7168 | 171.7168 | 171.7168 | 171.7168 | 171.7168 | 171.7168 | 171.7168 | 173.434 | 173.434 | 173.434 | 173.434 | 173.434 | 173.434 | 173.434 | 173.434 | 173.434 | 173.434 | 173.434 | 173.434 | 175.1683 | 175.1683 | 175.1683 | 175.1683 | 175.1683 | 175.1683 | 175.1683 | 175.1683 | 175.1683 | 175.1683 | 175.1683 | 175.1683 | 176.92
Snow Removal, Grass, Garbage | 1916.6667 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2034.5803
Janitor | 1916.6667 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1935.8333 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1955.1917 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1974.7436 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 1994.491 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2014.4359 | 2034.5803
Cleaning Reserve on Turnover | 637.5 | 643.875 | 643.875 | 643.875 | 643.875 | 643.875 | 643.875 | 643.875 | 643.875 | 643.875 | 643.875 | 643.875 | 643.875 | 650.3138 | 650.3138 | 650.3138 | 650.3138 | 650.3138 | 650.3138 | 650.3138 | 650.3138 | 650.3138 | 650.3138 | 650.3138 | 650.3138 | 656.8169 | 656.8169 | 656.8169 | 656.8169 | 656.8169 | 656.8169 | 656.8169 | 656.8169 | 656.8169 | 656.8169 | 656.8169 | 656.8169 | 663.3851 | 663.3851 | 663.3851 | 663.3851 | 663.3851 | 663.3851 | 663.3851 | 663.3851 | 663.3851 | 663.3851 | 663.3851 | 663.3851 | 670.0189 | 670.0189 | 670.0189 | 670.0189 | 670.0189 | 670.0189 | 670.0189 | 670.0189 | 670.0189 | 670.0189 | 670.0189 | 670.0189 | 676.7191
Security & Monitoring | 750 | 757.5 | 757.5 | 757.5 | 757.5 | 757.5 | 757.5 | 757.5 | 757.5 | 757.5 | 757.5 | 757.5 | 757.5 | 765.075 | 765.075 | 765.075 | 765.075 | 765.075 | 765.075 | 765.075 | 765.075 | 765.075 | 765.075 | 765.075 | 765.075 | 772.7257 | 772.7257 | 772.7257 | 772.7257 | 772.7257 | 772.7257 | 772.7257 | 772.7257 | 772.7257 | 772.7257 | 772.7257 | 772.7257 | 780.453 | 780.453 | 780.453 | 780.453 | 780.453 | 780.453 | 780.453 | 780.453 | 780.453 | 780.453 | 780.453 | 780.453 | 788.2575 | 788.2575 | 788.2575 | 788.2575 | 788.2575 | 788.2575 | 788.2575 | 788.2575 | 788.2575 | 788.2575 | 788.2575 | 788.2575 | 796.1401
Internet Expense | 1666.6667 | 1683.3333 | 1683.3333 | 1683.3333 | 1683.3333 | 1683.3333 | 1683.3333 | 1683.3333 | 1683.3333 | 1683.3333 | 1683.3333 | 1683.3333 | 1683.3333 | 1700.1667 | 1700.1667 | 1700.1667 | 1700.1667 | 1700.1667 | 1700.1667 | 1700.1667 | 1700.1667 | 1700.1667 | 1700.1667 | 1700.1667 | 1700.1667 | 1717.1683 | 1717.1683 | 1717.1683 | 1717.1683 | 1717.1683 | 1717.1683 | 1717.1683 | 1717.1683 | 1717.1683 | 1717.1683 | 1717.1683 | 1717.1683 | 1734.34 | 1734.34 | 1734.34 | 1734.34 | 1734.34 | 1734.34 | 1734.34 | 1734.34 | 1734.34 | 1734.34 | 1734.34 | 1734.34 | 1751.6834 | 1751.6834 | 1751.6834 | 1751.6834 | 1751.6834 | 1751.6834 | 1751.6834 | 1751.6834 | 1751.6834 | 1751.6834 | 1751.6834 | 1751.6834 | 1769.2003
EV Charging Expense | 416.6667 | 420.8333 | 420.8333 | 420.8333 | 420.8333 | 420.8333 | 420.8333 | 420.8333 | 420.8333 | 420.8333 | 420.8333 | 420.8333 | 420.8333 | 425.0417 | 425.0417 | 425.0417 | 425.0417 | 425.0417 | 425.0417 | 425.0417 | 425.0417 | 425.0417 | 425.0417 | 425.0417 | 425.0417 | 429.2921 | 429.2921 | 429.2921 | 429.2921 | 429.2921 | 429.2921 | 429.2921 | 429.2921 | 429.2921 | 429.2921 | 429.2921 | 429.2921 | 433.585 | 433.585 | 433.585 | 433.585 | 433.585 | 433.585 | 433.585 | 433.585 | 433.585 | 433.585 | 433.585 | 433.585 | 437.9209 | 437.9209 | 437.9209 | 437.9209 | 437.9209 | 437.9209 | 437.9209 | 437.9209 | 437.9209 | 437.9209 | 437.9209 | 437.9209 | 442.3001
Electricity (Common) | 1016.6667 | 1026.8333 | 1026.8333 | 1026.8333 | 1026.8333 | 1026.8333 | 1026.8333 | 1026.8333 | 1026.8333 | 1026.8333 | 1026.8333 | 1026.8333 | 1026.8333 | 1037.1017 | 1037.1017 | 1037.1017 | 1037.1017 | 1037.1017 | 1037.1017 | 1037.1017 | 1037.1017 | 1037.1017 | 1037.1017 | 1037.1017 | 1037.1017 | 1047.4727 | 1047.4727 | 1047.4727 | 1047.4727 | 1047.4727 | 1047.4727 | 1047.4727 | 1047.4727 | 1047.4727 | 1047.4727 | 1047.4727 | 1047.4727 | 1057.9474 | 1057.9474 | 1057.9474 | 1057.9474 | 1057.9474 | 1057.9474 | 1057.9474 | 1057.9474 | 1057.9474 | 1057.9474 | 1057.9474 | 1057.9474 | 1068.5269 | 1068.5269 | 1068.5269 | 1068.5269 | 1068.5269 | 1068.5269 | 1068.5269 | 1068.5269 | 1068.5269 | 1068.5269 | 1068.5269 | 1068.5269 | 1079.2122
Administration (% of EGI) | 3666.9306 | 3739.0531 | 3739.0531 | 3739.0531 | 3739.0531 | 3739.0531 | 3739.0531 | 3739.0531 | 3739.0531 | 3739.0531 | 3739.0531 | 3739.0531 | 3739.0531 | 3812.5998 | 3812.5998 | 3812.5998 | 3812.5998 | 3812.5998 | 3812.5998 | 3812.5998 | 3812.5998 | 3812.5998 | 3812.5998 | 3812.5998 | 3812.5998 | 3887.5989 | 3887.5989 | 3887.5989 | 3887.5989 | 3887.5989 | 3887.5989 | 3887.5989 | 3887.5989 | 3887.5989 | 3887.5989 | 3887.5989 | 3887.5989 | 3964.0792 | 3964.0792 | 3964.0792 | 3964.0792 | 3964.0792 | 3964.0792 | 3964.0792 | 3964.0792 | 3964.0792 | 3964.0792 | 3964.0792 | 3964.0792 | 4042.07 | 4042.07 | 4042.07 | 4042.07 | 4042.07 | 4042.07 | 4042.07 | 4042.07 | 4042.07 | 4042.07 | 4042.07 | 4042.07 | 4121.6013
Appliance & Furniture Reserve | 3733.3333 | 3770.6667 | 3770.6667 | 3770.6667 | 3770.6667 | 3770.6667 | 3770.6667 | 3770.6667 | 3770.6667 | 3770.6667 | 3770.6667 | 3770.6667 | 3770.6667 | 3808.3733 | 3808.3733 | 3808.3733 | 3808.3733 | 3808.3733 | 3808.3733 | 3808.3733 | 3808.3733 | 3808.3733 | 3808.3733 | 3808.3733 | 3808.3733 | 3846.4571 | 3846.4571 | 3846.4571 | 3846.4571 | 3846.4571 | 3846.4571 | 3846.4571 | 3846.4571 | 3846.4571 | 3846.4571 | 3846.4571 | 3846.4571 | 3884.9216 | 3884.9216 | 3884.9216 | 3884.9216 | 3884.9216 | 3884.9216 | 3884.9216 | 3884.9216 | 3884.9216 | 3884.9216 | 3884.9216 | 3884.9216 | 3923.7709 | 3923.7709 | 3923.7709 | 3923.7709 | 3923.7709 | 3923.7709 | 3923.7709 | 3923.7709 | 3923.7709 | 3923.7709 | 3923.7709 | 3923.7709 | 3963.0086
Structural Reserve | 916.7327 | 944.1109 | 944.1109 | 944.1109 | 944.1109 | 944.1109 | 944.1109 | 944.1109 | 944.1109 | 944.1109 | 944.1109 | 944.1109 | 944.1109 | 972.3083 | 972.3083 | 972.3083 | 972.3083 | 972.3083 | 972.3083 | 972.3083 | 972.3083 | 972.3083 | 972.3083 | 972.3083 | 972.3083 | 1001.3493 | 1001.3493 | 1001.3493 | 1001.3493 | 1001.3493 | 1001.3493 | 1001.3493 | 1001.3493 | 1001.3493 | 1001.3493 | 1001.3493 | 1001.3493 | 1031.2592 | 1031.2592 | 1031.2592 | 1031.2592 | 1031.2592 | 1031.2592 | 1031.2592 | 1031.2592 | 1031.2592 | 1031.2592 | 1031.2592 | 1031.2592 | 1062.0641 | 1062.0641 | 1062.0641 | 1062.0641 | 1062.0641 | 1062.0641 | 1062.0641 | 1062.0641 | 1062.0641 | 1062.0641 | 1062.0641 | 1062.0641 | 1093.7907
TOTAL OPERATING EXPENSES | 32745.2466 | 33013.1132 | 33013.1132 | 33013.1132 | 33013.1132 | 33013.1132 | 33013.1132 | 33013.1132 | 33013.1132 | 33013.1132 | 33013.1132 | 33013.1132 | 33013.1132 | 33284.9067 | 33284.9067 | 33284.9067 | 33284.9067 | 33284.9067 | 33284.9067 | 33284.9067 | 33284.9067 | 33284.9067 | 33284.9067 | 33284.9067 | 33284.9067 | 33560.6968 | 33560.6968 | 33560.6968 | 33560.6968 | 33560.6968 | 33560.6968 | 33560.6968 | 33560.6968 | 33560.6968 | 33560.6968 | 33560.6968 | 33560.6968 | 33840.5545 | 33840.5545 | 33840.5545 | 33840.5545 | 33840.5545 | 33840.5545 | 33840.5545 | 33840.5545 | 33840.5545 | 33840.5545 | 33840.5545 | 33840.5545 | 34124.5524 | 34124.5524 | 34124.5524 | 34124.5524 | 34124.5524 | 34124.5524 | 34124.5524 | 34124.5524 | 34124.5524 | 34124.5524 | 34124.5524 | 34124.5524 | 34412.7645
EBITDA / NOI
Net Operating Income | 89485.7734 | 91621.9897 | 91621.9897 | 91621.9897 | 91621.9897 | 91621.9897 | 91621.9897 | 91621.9897 | 91621.9897 | 91621.9897 | 91621.9897 | 91621.9897 | 91621.9897 | 93801.7527 | 93801.7527 | 93801.7527 | 93801.7527 | 93801.7527 | 93801.7527 | 93801.7527 | 93801.7527 | 93801.7527 | 93801.7527 | 93801.7527 | 93801.7527 | 96025.933 | 96025.933 | 96025.933 | 96025.933 | 96025.933 | 96025.933 | 96025.933 | 96025.933 | 96025.933 | 96025.933 | 96025.933 | 96025.933 | 98295.4187 | 98295.4187 | 98295.4187 | 98295.4187 | 98295.4187 | 98295.4187 | 98295.4187 | 98295.4187 | 98295.4187 | 98295.4187 | 98295.4187 | 98295.4187 | 100611.1153 | 100611.1153 | 100611.1153 | 100611.1153 | 100611.1153 | 100611.1153 | 100611.1153 | 100611.1153 | 100611.1153 | 100611.1153 | 100611.1153 | 100611.1153 | 102973.9461
DEBT SERVICE
Interest | 0 | 59216.6667 | 59182.9232 | 59149.0745 | 59115.1203 | 59081.0603 | 59046.8942 | 59012.6215 | 58978.2421 | 58943.7555 | 58909.1614 | 58874.4595 | 58839.6495 | 58804.7309 | 58769.7036 | 58734.567 | 58699.321 | 58663.9651 | 58628.499 | 58592.9223 | 58557.2348 | 58521.4361 | 58485.5258 | 58449.5036 | 58413.3691 | 58377.1219 | 58340.7618 | 58304.2884 | 58267.7014 | 58231.0002 | 58194.1847 | 58157.2545 | 58120.2092 | 58083.0484 | 58045.7717 | 58008.3789 | 57970.8696 | 57933.2434 | 57895.4999 | 57857.6387 | 57819.6596 | 57781.5621 | 57743.3458 | 57705.0104 | 57666.5556 | 57627.9809 | 57589.286 | 57550.4705 | 57511.534 | 57472.4762 | 57433.2966 | 57393.9949 | 57354.5708 | 57315.0237 | 57275.3534 | 57235.5595 | 57195.6416 | 57155.5992 | 57115.432 | 57075.1397 | 57034.7217 | 0
Principal Repayment | 0 | 10826.7936 | 10860.5371 | 10894.3858 | 10928.34 | 10962.4 | 10996.5661 | 11030.8387 | 11065.2182 | 11099.7048 | 11134.2989 | 11169.0008 | 11203.8108 | 11238.7294 | 11273.7567 | 11308.8933 | 11344.1393 | 11379.4952 | 11414.9613 | 11450.538 | 11486.2255 | 11522.0242 | 11557.9345 | 11593.9567 | 11630.0912 | 11666.3384 | 11702.6984 | 11739.1719 | 11775.7589 | 11812.4601 | 11849.2756 | 11886.2058 | 11923.2511 | 11960.4119 | 11997.6886 | 12035.0814 | 12072.5907 | 12110.2169 | 12147.9604 | 12185.8216 | 12223.8007 | 12261.8982 | 12300.1145 | 12338.4498 | 12376.9047 | 12415.4794 | 12454.1743 | 12492.9898 | 12531.9263 | 12570.9841 | 12610.1637 | 12649.4654 | 12688.8895 | 12728.4366 | 12768.1069 | 12807.9008 | 12847.8187 | 12887.8611 | 12928.0283 | 12968.3206 | 13008.7386 | 0
Total Debt Service | 0 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 70043.4603 | 0
CASH FLOW AFTER DEBT SERVICE | 89485.7734 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 102973.9461
CASH MANAGEMENT
Opening Cash Balance | 0 | 89485.7734 | 111064.3029 | 132642.8323 | 100000 | 121578.5294 | 143157.0589 | 100000 | 121578.5294 | 143157.0589 | 100000 | 121578.5294 | 143157.0589 | 100000 | 123758.2924 | 147516.5848 | 100000 | 123758.2924 | 147516.5848 | 100000 | 123758.2924 | 147516.5848 | 100000 | 123758.2924 | 147516.5848 | 100000 | 125982.4727 | 151964.9455 | 100000 | 125982.4727 | 151964.9455 | 100000 | 125982.4727 | 151964.9455 | 100000 | 125982.4727 | 151964.9455 | 100000 | 128251.9584 | 156503.9169 | 100000 | 128251.9584 | 156503.9169 | 100000 | 128251.9584 | 156503.9169 | 100000 | 128251.9584 | 156503.9169 | 100000 | 130567.655 | 161135.31 | 100000 | 130567.655 | 161135.31 | 100000 | 130567.655 | 161135.31 | 100000 | 130567.655 | 161135.31 | 100000
Cash Flow In Period | 89485.7734 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 21578.5294 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 23758.2924 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 25982.4727 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 28251.9584 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 30567.655 | 102973.9461
Available for Distribution | 0 | 11064.3029 | 32642.8323 | 54221.3618 | 21578.5294 | 43157.0589 | 64735.5883 | 21578.5294 | 43157.0589 | 64735.5883 | 21578.5294 | 43157.0589 | 64735.5883 | 23758.2924 | 47516.5848 | 71274.8772 | 23758.2924 | 47516.5848 | 71274.8772 | 23758.2924 | 47516.5848 | 71274.8772 | 23758.2924 | 47516.5848 | 71274.8772 | 25982.4727 | 51964.9455 | 77947.4182 | 25982.4727 | 51964.9455 | 77947.4182 | 25982.4727 | 51964.9455 | 77947.4182 | 25982.4727 | 51964.9455 | 77947.4182 | 28251.9584 | 56503.9169 | 84755.8753 | 28251.9584 | 56503.9169 | 84755.8753 | 28251.9584 | 56503.9169 | 84755.8753 | 28251.9584 | 56503.9169 | 84755.8753 | 30567.655 | 61135.31 | 91702.965 | 30567.655 | 61135.31 | 91702.965 | 30567.655 | 61135.31 | 91702.965 | 30567.655 | 61135.31 | 91702.965 | 102973.9461
Distribution | 0 | 0 | 0 | 54221.3618 | 0 | 0 | 64735.5883 | 0 | 0 | 64735.5883 | 0 | 0 | 64735.5883 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0
Closing Cash Balance | 89485.7734 | 111064.3029 | 132642.8323 | 100000 | 121578.5294 | 143157.0589 | 100000 | 121578.5294 | 143157.0589 | 100000 | 121578.5294 | 143157.0589 | 100000 | 123758.2924 | 147516.5848 | 100000 | 123758.2924 | 147516.5848 | 100000 | 123758.2924 | 147516.5848 | 100000 | 123758.2924 | 147516.5848 | 100000 | 125982.4727 | 151964.9455 | 100000 | 125982.4727 | 151964.9455 | 100000 | 125982.4727 | 151964.9455 | 100000 | 125982.4727 | 151964.9455 | 100000 | 128251.9584 | 156503.9169 | 100000 | 128251.9584 | 156503.9169 | 100000 | 128251.9584 | 156503.9169 | 100000 | 128251.9584 | 156503.9169 | 100000 | 130567.655 | 161135.31 | 100000 | 130567.655 | 161135.31 | 100000 | 130567.655 | 161135.31 | 100000 | 130567.655 | 161135.31 | 100000 | 202973.9461
WATERFALL DISTRIBUTION
Quarterly Distribution Amount | 0 | 0 | 0 | 54221.3618 | 0 | 0 | 64735.5883 | 0 | 0 | 64735.5883 | 0 | 0 | 64735.5883 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0
Tier 1: Preferred Return | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tier 2: Return of Capital | 0 | 0 | 0 | 54221.3618 | 0 | 0 | 64735.5883 | 0 | 0 | 64735.5883 | 0 | 0 | 64735.5883 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0
Tier 3: Profit Split | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Class E (LP) Share | 0 | 0 | 0 | 54221.3618 | 0 | 0 | 64735.5883 | 0 | 0 | 64735.5883 | 0 | 0 | 64735.5883 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 71274.8772 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 77947.4182 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 84755.8753 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0 | 0 | 91702.965 | 0
Class A (GP) Share | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Capital Returned | 0 | 0 | 0 | 54221.3618 | 54221.3618 | 54221.3618 | 118956.9501 | 118956.9501 | 118956.9501 | 183692.5384 | 183692.5384 | 183692.5384 | 248428.1268 | 248428.1268 | 248428.1268 | 319703.004 | 319703.004 | 319703.004 | 390977.8812 | 390977.8812 | 390977.8812 | 462252.7584 | 462252.7584 | 462252.7584 | 533527.6356 | 533527.6356 | 533527.6356 | 611475.0538 | 611475.0538 | 611475.0538 | 689422.472 | 689422.472 | 689422.472 | 767369.8903 | 767369.8903 | 767369.8903 | 845317.3085 | 845317.3085 | 845317.3085 | 930073.1838 | 930073.1838 | 930073.1838 | 1014829.0592 | 1014829.0592 | 1014829.0592 | 1099584.9345 | 1099584.9345 | 1099584.9345 | 1184340.8098 | 1184340.8098 | 1184340.8098 | 1276043.7749 | 1276043.7749 | 1276043.7749 | 1367746.7399 | 1367746.7399 | 1367746.7399 | 1459449.7049 | 1459449.7049 | 1459449.7049 | 1551152.67 | 1551152.67
Unreturned LP Capital | 2800000 | 2800000 | 2800000 | 2745778.6382 | 2745778.6382 | 2745778.6382 | 2681043.0499 | 2681043.0499 | 2681043.0499 | 2616307.4616 | 2616307.4616 | 2616307.4616 | 2551571.8732 | 2551571.8732 | 2551571.8732 | 2480296.996 | 2480296.996 | 2480296.996 | 2409022.1188 | 2409022.1188 | 2409022.1188 | 2337747.2416 | 2337747.2416 | 2337747.2416 | 2266472.3644 | 2266472.3644 | 2266472.3644 | 2188524.9462 | 2188524.9462 | 2188524.9462 | 2110577.528 | 2110577.528 | 2110577.528 | 2032630.1097 | 2032630.1097 | 2032630.1097 | 1954682.6915 | 1954682.6915 | 1954682.6915 | 1869926.8162 | 1869926.8162 | 1869926.8162 | 1785170.9408 | 1785170.9408 | 1785170.9408 | 1700415.0655 | 1700415.0655 | 1700415.0655 | 1615659.1902 | 1615659.1902 | 1615659.1902 | 1523956.2251 | 1523956.2251 | 1523956.2251 | 1432253.2601 | 1432253.2601 | 1432253.2601 | 1340550.2951 | 1340550.2951 | 1340550.2951 | 1248847.33 | 1248847.33

## O_Annual Summary
OPERATING PROFORMA - ANNUAL SUMMARY
Operating Year | 1 | 2 | 3 | 4 | 5 | 6 | Total | Disposition
Period | Mar 27 - Mar 27 | Apr 27 - Mar 28 | Apr 28 - Mar 29 | Apr 29 - Mar 30 | Apr 30 - Mar 31 | Apr 31 - Mar 32 |  | Exit / Sale
Months in Year | 1 | 12 | 12 | 12 | 12 | 12
REVENUE
Gross Rental Income | 121408 | 1486033.92 | 1515754.5984 | 1546069.6904 | 1576991.0842 | 1608530.9059 | 7854788.1988
Internet Revenue | 3200 | 38976 | 39560.64 | 40154.0496 | 40756.3603 | 41367.7057 | 204014.7557
Parking Revenue | 3525 | 42934.5 | 43578.5175 | 44232.1953 | 44895.6782 | 45569.1134 | 224735.0043
EV Charging Revenue | 1900 | 23142 | 23489.13 | 23841.4669 | 24199.089 | 24562.0753 | 121133.7612
Total Service Revenue | 8625 | 105052.5 | 106628.2875 | 108227.7118 | 109851.1275 | 111498.8944 | 549883.5212
GROSS POTENTIAL REVENUE | 130033 | 1591086.42 | 1622382.8859 | 1654297.4022 | 1686842.2117 | 1720029.8003 | 8404671.72 | 26829630.7487 | 26829630.7487
Vacancy & Bad Debt | -7801.98 | -95465.1852 | -97342.9732 | -99257.8441 | -101210.5327 | -103201.788 | -504280.3032
EFFECTIVE GROSS INCOME | 122231.02 | 1495621.2348 | 1525039.9127 | 1555039.558 | 1585631.679 | 1616828.0122 | 7900391.4168
OPERATING EXPENSES
Municipal Taxes | 9375 | 112500 | 112500 | 112500 | 112500 | 112500 | 571875
School Taxes | 1950 | 23400 | 23400 | 23400 | 23400 | 23400 | 118950
Insurance | 1415.75 | 17158.89 | 17330.4789 | 17503.7837 | 17678.8215 | 17855.6097 | 88943.3339
Repairs & Maintenance | 3200 | 38784 | 39171.84 | 39563.5584 | 39959.194 | 40358.7859 | 201037.3783
Outdoor Amenities Maintenance | 166.6667 | 2020 | 2040.2 | 2060.602 | 2081.208 | 2102.0201 | 10470.6968
Snow Removal, Grass, Garbage | 1916.6667 | 23230 | 23462.3 | 23696.923 | 23933.8922 | 24173.2312 | 120413.013
Janitor | 1916.6667 | 23230 | 23462.3 | 23696.923 | 23933.8922 | 24173.2312 | 120413.013
Cleaning Reserve on Turnover | 637.5 | 7726.5 | 7803.765 | 7881.8027 | 7960.6207 | 8040.2269 | 40050.4152
Security & Monitoring | 750 | 9090 | 9180.9 | 9272.709 | 9365.4361 | 9459.0905 | 47118.1355
Internet Expense | 1666.6667 | 20200 | 20402 | 20606.02 | 20812.0802 | 21020.201 | 104706.9679
EV Charging Expense | 416.6667 | 5050 | 5100.5 | 5151.505 | 5203.02 | 5255.0503 | 26176.742
Electricity (Common) | 1016.6667 | 12322 | 12445.22 | 12569.6722 | 12695.3689 | 12822.3226 | 63871.2504
Administration (% of EGI) | 3666.9306 | 44868.637 | 45751.1974 | 46651.1867 | 47568.9504 | 48504.8404 | 237011.7425
Appliance & Furniture Reserve | 3733.3333 | 45248 | 45700.48 | 46157.4848 | 46619.0596 | 47085.2502 | 234543.608
Structural Reserve | 916.7327 | 11329.3309 | 11667.6991 | 12016.1911 | 12375.1101 | 12744.7687 | 61049.8325
TOTAL OPERATING EXPENSES | 32745.2466 | 396157.3579 | 399418.8804 | 402728.3616 | 406086.6541 | 409494.6286 | 2046631.1291 | 268296.3075 | 268296.3075
EBITDA / NOI
Net Operating Income | 89485.7734 | 1099463.8769 | 1125621.0324 | 1152311.1965 | 1179545.0249 | 1207333.3837 | 5853760.2877 | 26561334.4412 | 26561334.4412
DEBT SERVICE
Interest | 0 | 708349.6287 | 703320.7781 | 698100.5909 | 692681.7869 | 687056.8093 | 3489509.5939
Principal Repayment | 0 | 132171.8949 | 137200.7454 | 142420.9327 | 147839.7367 | 153464.7142 | 713098.0238
Total Debt Service | 0 | 840521.5236 | 840521.5236 | 840521.5236 | 840521.5236 | 840521.5236 | 4202607.6178 | 18286901.9762 | 18286901.9762
CASH FLOW AFTER DEBT SERVICE | 89485.7734 | 258942.3534 | 285099.5088 | 311789.6729 | 339023.5013 | 366811.8601 | 1651152.67 | 8274432.465 | 8274432.465
CASH MANAGEMENT
Opening Cash Balance | 0 | 89485.7734 | 100000 | 100000 | 100000 | 100000 | 0
Cash Flow In Period | 89485.7734 | 258942.3534 | 285099.5088 | 311789.6729 | 339023.5013 | 366811.8601 | 1651152.67
Available for Distribution | 0 | 486342.027 | 570199.0176 | 623579.3459 | 678047.0027 | 733623.7203 | 3091791.1134
Distribution | 0 | 248428.1268 | 285099.5088 | 311789.6729 | 339023.5013 | 366811.8601 | 1551152.67
Closing Cash Balance | 89485.7734 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
WATERFALL DISTRIBUTION
Quarterly Distribution Amount | 0 | 248428.1268 | 285099.5088 | 311789.6729 | 339023.5013 | 366811.8601 | 1551152.67 | 8274432.465 | 8274432.465
Tier 1: Preferred Return | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tier 2: Return of Capital | 0 | 248428.1268 | 285099.5088 | 311789.6729 | 339023.5013 | 366811.8601 | 1551152.67 | 1248847.33 | 1248847.33
Tier 3: Profit Split | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7025585.135 | 7025585.135
Class E (LP) Share | 0 | 248428.1268 | 285099.5088 | 311789.6729 | 339023.5013 | 366811.8601 | 1551152.67 | 6166756.9245 | 6166756.9245
Class A (GP) Share | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2107675.5405 | 2107675.5405
Cumulative Capital Returned | 0 | 248428.1268 | 533527.6356 | 845317.3085 | 1184340.8098 | 1551152.67 | 1551152.67 | 2800000 | 2800000
Unreturned LP Capital | 2800000 | 2551571.8732 | 2266472.3644 | 1954682.6915 | 1615659.1902 | 1248847.33 | 1248847.33 | 0 | 0
Year-End Month # | 25 | 37 | 49 | 61 | 73 | 85
Year-End Loan Balance | 0 | 18867828.1051 | 18730627.3597 | 18588206.427 | 18440366.6904 | 18286901.9762 |  | 18286901.9762 | 18286901.9762
KEY PERFORMANCE INDICATORS
RETURN METRICS
Cash-on-Cash Return | 3.196% | 9.248% | 10.18% | 11.14% | 12.11% | 13.1%
Yield-on-Cost | 2.465% | 2.524% | 2.584% | 2.645% | 2.708% | 2.771%
Equity Multiple (Cumulative) | 0 | 0.088724 | 0.19055 | 0.3019 | 0.42298 | 0.55398 |  | 3.5091
Cash Flow % (CFADS/EGI) | 73.21% | 17.31% | 18.69% | 20.05% | 21.38% | 22.69% |  |  | 2.9552
Project IRR (Levered) | N/A | N/A | 41.77% | 35.4% | 31.52% | 35.46% | 35.46% | 35.46%
Project IRR (Levered) |  | N/A | N/A | 41.77% | 35.4% | 35.46% |  | 35.46% | 35.46%
Class E (LP) IRR |  | N/A | N/A | 32.01% | 27.77% | 29.98% |  | 29.98% | 29.98%
DEBT METRICS
Debt Service Coverage Ratio (DSCR) | - | 1.3081 | 1.3392 | 1.3709 | 1.4033 | 1.4364
Interest Coverage Ratio (ICR) | - | 1.5521 | 1.6004 | 1.6506 | 1.7029 | 1.7573
Loan-to-Value (LTV) | 0% | 77.22% | 74.88% | 72.59% | 70.35% | 68.16%
Debt Yield | - | 5.827% | 6.01% | 6.199% | 6.397% | 6.602%
EXPENSE METRICS
Operating Expense Ratio | 26.79% | 26.49% | 26.19% | 25.9% | 25.61% | 25.33%
Net Operating Margin | 73.21% | 73.51% | 73.81% | 74.1% | 74.39% | 74.67%
PER-UNIT METRICS
Revenue per Unit (Annualized) | 24381.1875 | 24860.7253 | 25349.7326 | 25848.3969 | 26356.9096 | 26875.4656
OPEX per Unit (Annualized) | 6139.7337 | 6189.9587 | 6240.92 | 6292.6306 | 6345.104 | 6398.3536
NOI per Unit (Annualized) | 16778.5825 | 17179.1231 | 17587.8286 | 18004.8624 | 18430.391 | 18864.5841
CFADS per Unit (Annualized) | 16778.5825 | 4045.9743 | 4454.6798 | 4871.7136 | 5297.2422 | 5731.4353
DISPOSITION CALCULATIONS
Annualized Year 6 NOI | 1207333.3837
Exit Cap Rate | 4.5%
Gross Sale Price | 26829630.7487
Disposition Costs | 268296.3075
Net Sale Proceeds | 26561334.4412
Loan Payoff (Balance at Maturity) | 18286901.9762
Net Equity Proceeds | 8274432.465
DISPOSITION WATERFALL
Net Equity Proceeds | 8274432.465
Unreturned LP Capital (at exit) | 1248847.33
Tier 1: Final Preferred Return | 0
Tier 2: Return of Remaining Capital | 1248847.33
Tier 3: Profit Split | 7025585.135
Class E (LP) Distribution | 6166756.9245
Class A (GP) Distribution | 2107675.5405
Check (LP+GP = Net Proceeds) | 0
Project IRR CF (exit Y3) | -2800000 | 248428.1268 | 285099.5088 | 7074429.5685
Project IRR CF (exit Y4) | -2800000 | 248428.1268 | 285099.5088 | 311789.6729 | 7848647.3586
Project IRR CF (exit Y5) | -2800000 | 248428.1268 | 285099.5088 | 311789.6729 | 339023.5013 | 8641244.3252
Project IRR CF (full hold) | -2800000 | 248428.1268 | 285099.5088 | 311789.6729 | 339023.5013 | 10192396.9951
LP IRR CF (exit Y3) | -2800000 | 248428.1268 | 285099.5088 | 5632042.4073
LP IRR CF (exit Y4) | -2800000 | 248428.1268 | 285099.5088 | 311789.6729 | 6080457.9585
LP IRR CF (exit Y5) | -2800000 | 248428.1268 | 285099.5088 | 311789.6729 | 339023.5013 | 6533568.7847
LP IRR CF (full hold) | -2800000 | 248428.1268 | 285099.5088 | 311789.6729 | 339023.5013 | 8084721.4546